# WORKPLAN – PROJECT RFW

| # PROJECT NAME | # PROJECT LEAD | # PROJECT START DATE | # PROJECT END DATE | # TODAY’S DATE |
| --- | --- | --- | --- | --- |
| # REDUCING FOREIGN WORKER | # ZAFFRULLA HUSSEIN | # 04 NOV 2022 | # FEB 2023 |  |

|  |  |  |  |  | Individual columns represent weeks. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | MONTH |  | NOV 2022 |  |  |  |  | DECEMBER 2022 |  |  |  |  | JANUARY 2023 |  |  |  |  | FEB 2023 |  |  |  |  |
|  |  |  | WEEK START DATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITY | % DONE | ASSIGNED TO | START DATE | END DATE | 6 | 13 | 20 | 27 |  | 4 | 11 | 18 | 25 |  | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 |  |
| WORKSHOP - AWARENESS |  |  | 24/11 | 24/11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Promotion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of diagnostic tool |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRE-DIAGNOSIC RESULT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| COMPANY SELECTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| VISIT/ ASSESSMENT (20 Cos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WORKSHOP – ROADMAP DEV. |  |  | 20/12 | 20/12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Guideline report – series of workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| VISIT/ ASSESSMENT (More Cos) – testing the guideline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Report / Finding Workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |