JADUAL PELAKSAAN & PEMBAYARAN

(SEKTOR PELANCONGAN 30 ORGANISASI – SESI 1 (Bulan Jan – Jun 2023)

| Phase | Number of Day(s) | Program / Activity | Hours | Rate/Hour (RM) | Total (RM) | Total Payment by Phase |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1 | ½ day | Program Briefing (Moderator) Malaysia Productivity Performance, the importance of PLWS to Management and Employees. Explain on the VT-PLWS Implementation. | 2 | 250.00 | 500.00 | Payment Phase 1 Trainer: RM4,100.00 Accommodation: RM21,000.00 TOTAL: RM25,100.00 Output Phase 1 Report on Companies Current Wage/ Compensation System (Health-check) |
|  | 1 day | Training Day 1 (Trainer) Enhancing Competitiveness Through Productivity Measurement Wage Transformation Through PLWS • PLWS Models & Components • SWOT Analysis & SMART Principle • Example of PLWS Creating Conducive Environment • Case Study on PLWS Implementation • Measuring companies’ productivity performance (i.e: Labour Productivity, Wages, Labour Cost Competitiveness & Unit Labour Cost) • Briefing on KPIs | 8 | 1,800.00 | 1,800.00 |  |
|  | 1 day | Training Day 2 (Trainer) Establishing PLWS • Developing companies’ KPIs. • Linking Performance with Incentives • Obtain Feedback on the measurement. Implement PLWS • Developing PLWS models. • Develop types of Incentives. | 8 | 1,800.00 | 1,800.00 |  |
| Phase 2 | 15 days | Virtual Handholding Session (Trainer) One to one session with each company (2hrs per company x 30 companies) 2 companies per day | 2 hours x 15 days = 30 hours | 300.00 | 9,000.00 | Payment Phase 2 Trainer: RM9,000.00 TOTAL: RM9,000.00 Output Phase 2: Report on Companies Presentation Guidelines Through Handholding Session |
| Companies Preparation (Man-days depends on company) |  |  |  |  |  |  |
| Phase 3 | 1 day | Sharing Session – will be held physically 30 companies x 2 pax = 60 pax 1 Trainer 1 Moderator 4 Secretariat Sharing Session on PLWS Development by participated companies through Seminar. • Companies background, objectives, and benefits of program. • Company Productivity Performance. • PLWS Development by companies. • Timeline of the implementation. • QnA Session | 8 | 1,800.00 | 1,800.00 | Payment Phase 3 Trainer: RM1,800.00 Accommodations: RM10,500.00 TOTAL: RM12,300.00 Output Phase 3: Sharing Session of PLWS Implementation (Slide Presentation from each company) |
|  | 1 | Report Submission Final consultation to amend final report/slide development of PLWS. |  |  |  |  |
| TOTAL HOURS / TOTAL PAYMENT FOR TRAINER |  |  | 82 |  | 23,900.00 | RM46,400.00 |

JADUAL PELAKSAAN & PEMBAYARAN

(SEKTOR PERKHIDMATAN 30 ORGANISASI – SESI 2 (Bulan Jul – Dis 2023)

| Phase | Number of Day(s) | Program / Activity | Hours | Rate/Hour (RM) | Total (RM) | Total Payment by Phase |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1 | ½ day | Program Briefing (Moderator) Malaysia Productivity Performance, the importance of PLWS to Management and Employees. Explain on the VT-PLWS Implementation. | 2 | 250.00 | 500.00 | Payment Phase 1 Trainer: RM4,100.00 Accommodation: RM21,000.00 TOTAL: RM25,100.00 Output Phase 1 Report on Companies Current Wage/ Compensation System (Health-check) |
|  | 1 day | Training Day 1 (Trainer) Enhancing Competitiveness Through Productivity Measurement Wage Transformation Through PLWS • PLWS Models & Components • SWOT Analysis & SMART Principle • Example of PLWS Creating Conducive Environment • Case Study on PLWS Implementation • Measuring companies’ productivity performance (i.e: Labour Productivity, Wages, Labour Cost Competitiveness & Unit Labour Cost) • Briefing on KPIs | 8 | 1,800.00 | 1,800.00 |  |
|  | 1 day | Training Day 2 (Trainer) Establishing PLWS • Developing companies’ KPIs. • Linking Performance with Incentives • Obtain Feedback on the measurement. Implement PLWS • Developing PLWS models. • Develop types of Incentives. | 8 | 1,800.00 | 1,800.00 |  |
| Phase 2 | 15 days | Virtual Handholding Session (Trainer) One to one session with each company (2hrs per company x 30 companies) 2 companies per day | 2 hours x 15 days = 30 hours | 300.00 | 9,000.00 | Payment Phase 2 Trainer: RM9,000.00 TOTAL: RM9,000.00 Output Phase 2: Report on Companies Presentation Guidelines Through Handholding Session |
| Companies Preparation (Man-days depends on company) |  |  |  |  |  |  |
| Phase 3 | 1 day | Sharing Session – will be held physically 30 companies x 2 pax = 60 pax 1 Trainer 1 Moderator 4 Secretariat Sharing Session on PLWS Development by participated companies through Seminar. • Companies background, objectives, and benefits of program. • Company Productivity Performance. • PLWS Development by companies. • Timeline of the implementation. • QnA Session | 8 | 1,800.00 | 1,800.00 | Payment Phase 3 Trainer: RM1,800.00 Accommodations: RM10,500.00 TOTAL: RM12,300.00 Output Phase 3: Sharing Session of PLWS Implementation (Slide Presentation from each company) |
|  | 1 | Report Submission Final consultation to amend final report/slide development of PLWS. |  |  |  |  |
| TOTAL HOURS / TOTAL PAYMENT FOR TRAINER |  |  | 82 |  | 23,900.00 | RM46,400.00 |