PAPER FOR APPROVAL

MPC BOARD OF MANAGEMENT (BOM)

| TITLE | Accelerate Talent Development to Enhance the Competency Level of M&E Industry through Process Improvement Program: Train the Trainers |
| --- | --- |
| DATE / DURATION | February – May 2022 |
| BACKGROUND AND OBJECTIVES | Thrust 1 in MPB emphasizes on the development of Malaysian talent. This is a crucial step in building the workforce of the future. There is now an urgent need to align the mindset of all Malaysians to raise the number of highly skilled workers, reduce dependence on foreign workers, especially the low -skilled, and equip Malaysians with the necessary knowledge so that we can all be future ready. Hence, MEPN take intiative to set up partnership between the government and industry associations to up-skill existing employees with the objectives: - To provide industry process improvement knowledge to selected TVET trainers from MEIF-TVET Strategic Partners to enable them to impart such practical knowledge to students (future workforce); - To enhance the capabilities of the future workforces in Industry 4.0 transformation; and - To showcase the project best practices in national convention programmes. |
| METHODS OF IMPLEMENTATION | Activities will be conducted both physically and virtually through training, workshops and quality at source program. Note: Program details, please refer to Appendix 1 and 2. |
| STAKEHOLDERS | - NGC Private Sectors: Machinery & Engineering Industries Federation (MEIF) and associations under its umbrella. - NGC Public Sectors: EPU, MITI, MIDA, MATRADE, SIRIM, HRD Corp and ILMIA. - TVET institutions |
| EXPECTED OUTCOME | - Improving enterprise productivity and competitiveness ranking for existing employees as well as critical thinking in problem solving to ensure the marketability of students in the future. - Successful model in assisting M&E industry players to increase businesses productivity. |
| EXPECTED OUPUT | - 3-day workshop for trainers - 8 micro learnings for trainers - 20 trainers trained |
| TARGET GROUP | - Trainers: - MEIF-TVET strategic partners |
| BUDGET / ESTIMATED COST | MPB-MEPN; :; 34,000.00. Total; :; 34,000.00. Note: Budget details, please refer to Appendix 3. |
| INCOME (RM) IF ANY | - |
| RECOMMENDATION | The approval of BOM is sought to approve the budget of RM34,000.00 to utilize the MPB-MEPN budget for organising the program on Accelerate Talent Development to Enhance the Competency Level of M&E Industry through Process Improvement Program: Train The Trainers, February – May 2022. |
| UNIT / DIVISION | Machinery and Equipment Productivity Nexus (MEPN), Delivery Management Office (DMO) |

**Please attach other relevant information if necessary.

(Examples: Program agenda, cost details, risk plan, diagrams, plan sketches, name lists, Gantt charts, etc.)

Only for applications that use Development Budget from other Units/Divisions. This column can be ignored if it is not relevant.

SUPPORTED BY: NAME OF OFFICER IN CHARGE OF THE DEVELOPMENT BUDGET Position: Budget Name: Date:

| PREPARED BY: Abdul Rahman Kamis Assistant Manager Date: 31/1/2022 | CHECKED BY: Azhani Ismail Manager Date: 31/1/2022 | APPROVED BY: Dr. Mohamad Norjayadi Tamam Director Date: |
| --- | --- | --- |

APPENDIX 1

PROGRAM FLOW CHART

Accelerate Talent Development to Enhance the Competency Level of M&E Industry through Process Improvement Program

Manufacturing Apprentice

Quality at Source

Yes

Industry Ready Graduates

MPC Productivity Specialist

- Report

- Best Practices

- ARISE Project

Productivity Improvement Showcase

- Fill up P1010 (above 20%)

- Manufacturing companies

No

Engagement with stakeholders

Microlearning for TTT

Microlearning for Student

Practical/ Attachment

MyReskill IoT for technology improvement

Process/ Technique Improvement

Meeting with KISMEC on the program

GEMBA

(Fact Finding)

- GEMBA visit date

- Recruit practical student

MoU/ NDA signing with companies

Interview 5 selected companies

Screening MEVAC companies

10-Day Training

3-Day Training the Trainers

Invitation to TVET Strategic Partners

Confirmation on student for pilot test

- Company complete VSM template before visit

- VSM Report and Recommendation

The request budget to cover activities in the rectangle area

Launching Ceremony

APPENDIX 2

PROGRAM MILESTONE

Accelerate Talent Development to Enhance the Competency Level of M&E Industry through Process Improvement Program

| Item | Activities | Jan |  |  |  | Feb |  |  |  | Mac |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Program Kickstart |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. | Training (TTT) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. | Interview Session with Selected Companies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. | Training (Student) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. | MoU/ NDA Signing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. | Workshop for GEMBA and VSM Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. | Microlearning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. | GEMBA/ Fact Finding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. | Engagement with Stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10. | Launching Ceremony |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11. | Program Report for Mfg Apprentice |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12. | Workshop: Process Improvement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13. | Implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14. | Productivity Improvement Showcase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15. | Program Report for Quality at Source |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Manufacturing Apprentice

Quality at Source

Legend:

APPENDIX 3

BUDGET / ESTIMATED COST

Accelerate Talent Development to Enhance the Competency Level of M&E Industry through Process Improvement Program: Train the Trainers (TTT)

Table 1 : Estimated Partial Cost, February – May 2022

| No. | Item | Cost / Unit | Pax | Quantity | Total (RM) |
| --- | --- | --- | --- | --- | --- |
| - DEVELOPMENT BUDGET |  |  |  |  |  |
| - Project Administration |  |  |  |  |  |
| i. | Project Facilitator (TTT and Students) | RM250 | 2 | 20 hours | 10,000.00 |
| - Workshops (Train The Trainers) |  |  |  |  |  |
| i. | Trainer | RM2,000 | 1 | 3 days | 6,000.00 |
| ii. | Residential package | RM450.00 | 20 | 2 nights | 18,000.00 |
| - Video Recording & Microlearning Videos |  |  |  |  |  |
|  | Video recording during the TTT will be covered by Unit Penyiaran & Kandungan Digital | - | - | - | 0.00 |
| Total A |  |  |  |  | 34,000.00 |

Table 2 : Estimated Total Cost, January – December 2022

| No. | Item | Cost / Unit | Pax | Quantity | Total (RM) |
| --- | --- | --- | --- | --- | --- |
| - DEVELOPMENT BUDGET |  |  |  |  |  |
| - Project Administration |  |  |  |  |  |
| i. | Project Facilitator | RM250 | 2 | 40 hours | 20,000.00 |
| ii. | Industry Expert – Interview | RM400 | 1 | 5 | 2,000.00 |
| iii. | Press Release | RM1000 | 4 | 1 | 4,000.00 |
| - Workshops (Train The Trainers) |  |  |  |  |  |
| i. | Trainer | RM2,000 | 1 | 3 days | 6,000.00 |
| ii. | Residential package | RM450.00 | 20 | 2 night | 18,000.00 |
| - Train the Students |  |  |  |  |  |
| i. | Training Package - (trainer, accomodation, traning kits) |  |  | 10 days | 20,000.00 |
| ii. | Site visit (transportation) |  |  |  | 2,000.00 |
| - Workshop on GEMBA Framework and MoU/NDA |  |  |  |  |  |
| i. | Fullday Package | RM200 | 20 | 1 | 4,000.00 |
| ii. | Workshop Facilitator | RM250 | 1 | 5 hours | 1,250.00 |
| iii. | Industry Expert – Input | RM400 | 5 | 2 hours | 4,000.00 |
| - GEMBA at 5 Companies (Physical) |  |  |  |  |  |
| i. | Site Inspector (Expert cum Trainer cum Site Inspector) | RM2,000 (min 4 hrs) | 1 | 5 companies | 10,000.00 |
| ii. | Expert | RM400 | 5 | 10 hours | 20,000.00 |
| iii. | Best Practices Article | RM2000 | 1 | 5 | 10,000.00 |
| - Video Recording & Microlearning Videos |  |  |  |  |  |
| iii. | Video editing |  |  |  | 20,000.00 |
| - Launching Ceremony |  |  |  |  |  |
| i. | Ceremony ½ day package Launching (VIP: Menteri MITI) | RM200 | 100 | ½ day | 20,000.00 |
| ii. | Montage video |  |  |  | 20,000.00 |
| Total A |  |  |  |  | 181,250.00 |
| - OPERATIONAL BUDGET |  |  |  |  |  |
| 1. | Mileage Claim / Grab/ Teksi / Food Allowance | - | - | - | 10,000.00 |
| 2. | Accomodation | RM250 | 5 | 6 | 7,500.00 |
| Total B |  |  |  |  | 14,500.00 |
| Grand Total (A + B) |  |  |  |  | 195,750.00 |

Launching Ceremony