KERTAS CADANGAN UNTUK PERTIMBANGAN

LEMBAGA PENGURUSAN MPC

| TAJUK Keterangan: Tajuk Projek/ Cadangan | INITIATIVES TO ENHANCE MALAYSIA'S COMPETITIVENESS PERFORMANCE - INDICATOR REVIEW |
| --- | --- |
| TARIKH/ GARIS MASA Keterangan: Jadual mula dan akhir pelaksanaan projek/ cadangan | August 2023 – November 2023 |
| TUJUAN & LATAR BELAKANG Keterangan: Tujuan dan penerangan ringkas mengenai projek | Malaysia Productivity Corporation (MPC) has been mandated by the Public Service Department (JPA) to enhance the country's competitiveness in world competitiveness reports such as the World Competitiveness Yearbook (WCY), Global Competitiveness Report (GCR), and others. In line with this, MPC will undertake improvements involving several indicators of national competitiveness, namely Female Labor Force, Workforce, and Digitalisation, for the purpose of the country's economic recovery, sustainable economic growth, and significant productivity surge. These indicator improvements will be driven by the Sustainable Development Goals Technical Working Group (TWGSDG) under PEMUDAH, in collaboration with Ministries, Agencies, the private sector, and non-governmental organizations (NGOs). |
| JUSTIFIKASI Keterangan: Penjelasan yang menyokong kepada pelaksanaan projek/ cadangan | The establishment of TWGSDG under PEMUDAH has resulted in positive achievements in accelerating public-private sector initiatives in facilitating the way of doing business. The TWGSDG also aimed to create a sustainable and robust Care Economy to enhance the nation's productivity and competitiveness. The achievements will also be recognized by various international bodies including the World Bank, the World Economic Forum, and the Institute for Management Development (IMD). |
| KAEDAH PELAKSANAAN Keterangan: Kaedah yang perlu dilakukan bagi melaksanakan projek | - To study the World Competitiveness Ranking (WCR) Framework on indicator Female Labor Force, Digital, Workforce and provide specific recommendation especially which related to the care economy. - To analyse concerns raised by relevant stakeholders or affected parties regarding the indicators and to propose specific improvement to be implemented by the process owner thru a strategic engagement. - To monitor and report to PEMUDAH on the issues and outcomes encountered to enhance competitiveness of the country. |
| STAKEHOLDERS/ PIHAK BERKEPENTINGAN Keterangan: Pihak atau kumpulan yang menerima kesan positif mahupun negatif daripada projek yang dijalankan | - Ministries - Agencies - Local State Authority (PBT) - Business Association - Business Community |
| JANGKAAN HASIL/ OUTCOME Keterangan: Apa yang MPC perlu capai/ faedah-faedah jangka pendek dan jangka panjang hasil dari intervensi projek/ cadangan | - Well-informed regulators on matters relating to Sustainable Development Goals on designing public policy with related to specific indicators. - A sustainable and robust Care Economy to enhance the nation's productivity and competitiveness |
| JANGKAAN OUTPUT Keterangan:Output ketara dan tidak ketara yang dihasilkan daripada aktiviti projek/ cadangan. | - Report on the initiatives and activities of TWGSDG based on the improved indicators. |
| KUMPULAN SASAR Keterangan: Individu/ kumpulan yang menerima faedah daripada projek/ cadangan | - Ministries - Agencies - Local State Authority (PBT) - Business Association - Business Community |
| SUMBER BAJET/ KOS Keterangan: Sumber bajet / jumlah kos yang terlibat. | RM40,000 (Budget RM40 2023) |
| HASIL (RM) - SEKIRANYA ADA Keterangan: Pendapatan yang diterima daripada projek | N/A |
| SYOR Keterangan: Keputusan yang diperlukan daripada Lembaga Pengurusan MPC | The approval of the Board of Management (BOM) is sought for Initiatives To Enhance Malaysia's Competitiveness Performance - Indicator Review with total cost of RM40,000 utilising RM40 budget 2023. |
| UNIT/ BAHAGIAN | National Competitiveness Section/ PCD |

**Sila lampirkan maklumat-maklumat lain yang berkaitan sekiranya perlu.  (Contoh: Agenda program, perincian kos, pelan risiko, gambar rajah, lakaran pelan, senarai nama, carta Gantt, dll.

Estimated Cost

| No. | Phase | Item | Estimated Cost (Rm) | Total (Rm) |
| --- | --- | --- | --- | --- |
| 1. | Advocacy | Media Statement RM1,000 x 6 Media Statement | 6,000.00 | 6,000.00 |
| 2. | Advisory | Hiring of SME to Share Knowledge and Experience and Conduct Interviews with Selected Ministries/Agencies PBTS’s or Business Association. RM400 x 5 Hours = RM2,000 TWGSDG Initiatives and Activities - Facilitator /SME/Speaker RM2000 x 4 Days = RM8,000 | 10,000.00 | 10,000.00 |
| 3. | Promotion | Video And Promotional Items Interactive Video, Corporate, Public Service Announcement, Online Platform, Digital Content, Digital Publication, And Tools (Murals, Posters, Ebook, Database, etc) | 4,000.00 | 4,000.00 |
| 4. | Coordination | Engagements with Stakeholders (Events, Forums, Meeting Packages and Food & Beverages Meeting Attendees) | 20,000.00 | 20,000.00 |
| Total |  |  |  | 40,000.00 |

Hanya untuk permohonan yang menggunakan Bajet Pembangunan dari Unit/Bahagian lain. Kolum ini boleh diabaikan sekiranya tidak berkaitan.

DISOKONG OLEH: NAMA PEGAWAI PENJAGA BAJET PEMBANGUNAN Jawatan: Nama Bajet: Tarikh:

| **Wajib diisi | **Wajib diisi | Permohonan memadai disemak sehingga peringkat Penyelia. Kolum ini boleh diabaikan sekiranya tidak berkaitan |
| --- | --- | --- |
| DISEDIAKAN OLEH: SITI NUR SYUHAIDA Penolong Pengurus 16 Ogos 2023 | DISEMAK OLEH: NORHASIMAH IBRAHIM Timbalan Pengarah 16 Ogos 2023 | DISAHKAN OLEH: ALAMIN REHAN Pengarah 16 Ogos 2023 |

APPENDIX 1

| No | Activities/ Timeline | 2023 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Aug | Sept | Oct | Nov |
|  | Review study on indicators of WCR |  |  |  |  |
|  | Malaysia Care Economy Forum |  |  |  |  |
|  | Analyse concerns raised by relevant stakeholders or affected parties |  |  |  |  |
|  | TWGSDG Meeting No. 2/2023 |  |  |  |  |
|  | Project Experimentation |  |  |  |  |
|  | Presentation to PEMUDAH Private Sector |  |  |  |  |
|  | Review recommendation |  |  |  |  |
|  | Presentation to PEMUDAH |  |  |  |  |
|  | Presentation to stakeholders (Economy, KPWKM, MOF) |  |  |  |  |
|  | Preparation of report |  |  |  |  |