KERTAS CADANGAN UNTUK PERTIMBANGAN

LEMBAGA PENGURUSAN MPC (BOM)

| TAJUK Keterangan: Tajuk Projek/ Cadangan | DEVELOPMENT OF EASE OF DOING BUSINESS DOCUMENT |
| --- | --- |
| TARIKH/ GARIS MASA Keterangan: Jadual mula dan akhir pelaksanaan projek/ cadangan | Feb – June 2024 |
| TUJUAN & LATAR BELAKANG Keterangan: Tujuan dan penerangan ringkas mengenai projek | Government through the Special Taskforce to Facilitate Business (PEMUDAH) is currently in the process of formulating the ease of doing business document to enhance business confidence, boost productivity and competitiveness, stimulate economic growth and drive the digital transformation of the country. This document will outline strategies for ease of doing business including structural reforms towards boosting productivity and competitiveness and promoting sustainable economic growth. This document is developed in line with 10 topics based on the Business Ready (B-READY) framework by the World Bank. The development of the document comprises three chapter, which cover the following areas: - Chapter 1 : Location Benchmarking on Local Government and Land Matters; - Chapter 2 : 10 Elements as per World Bank’s B-Ready Report; and - Chapter 3 : Pertinent Challenges Beyond B-Ready Elements Each chapter shall identify relevant challenges and key reform initiatives in the respective area. |
| JUSTIFIKASI Keterangan: Penjelasan yang menyokong kepada pelaksanaan projek/ cadangan | The document aimed at addressing prevalent challenges and unlocking future growth opportunities for businesses in Malaysia towards boosting productivity, competitiveness, and a more prosperous economic growth. |
| KAEDAH PELAKSANAAN Keterangan: Kaedah yang perlu dilakukan bagi melaksanakan projek | - Engagement Session - Workshop - Report Writing |
| STAKEHOLDERS/ PIHAK BERKEPENTINGAN Keterangan: Pihak atau kumpulan yang menerima kesan positif mahupun negatif daripada projek yang dijalankan | - Business Associations - Ministry / Agencies |
| SUMBER BAJET/ KOS Keterangan: Sumber bajet / jumlah kos yang terlibat. | FORE: RM500,000.00 BIL.; PERKARA; KOS (RM). 1.; Facilitator & Moderator; 200,000.00. 2.; Report Writing & Editorial; 200,000.00. 3.; Design & Infographic; 100,000.00. TOTAL; 500,000.00. |
| HASIL (RM) - SEKIRANYA ADA Keterangan: Pendapatan yang diterima daripada projek | -NA- |
| SYOR Keterangan: Keputusan yang diperlukan daripada Lembaga Pengurusan MPC | The approval of the Board of Management (BOM) is sought for Development of Ease of Doing Business Document using FORE Budget (DE) amounting RM500,000.00. |
| UNIT/ BAHAGIAN | National Competitiveness Section (NCS)/ PCD |

**Sila lampirkan maklumat-maklumat lain yang berkaitan sekiranya perlu.

(Contoh: Agenda program, perincian kos, pelan risiko, gambar rajah, lakaran pelan, senarai nama, carta Gantt, dll.)

Hanya untuk permohonan yang menggunakan Bajet Pembangunan dari Unit/Bahagian lain. Kolum ini boleh diabaikan sekiranya tidak berkaitan.

DISOKONG OLEH: NAMA PEGAWAI PENJAGA BAJET PEMBANGUNAN Jawatan: Nama Bajet: Tarikh:

| **Wajib diisi | **Wajib diisi | Permohonan memadai disemak sehingga peringkat Penyelia. Kolum ini boleh diabaikan sekiranya tidak berkaitan |
| --- | --- | --- |
| DISEDIAKAN OLEH: NURUL AIN ALIA ABDULLAH ZAWAWI Pengurus 30 Januari 2024 | DISEMAK OLEH: SHAHRIZA BAHARI Timbalan Pengarah 30 Januari 2024 | DISAHKAN OLEH: WAN FAZLIN NADIA WAN OSMAN Pengarah |

ATTACHMENT 1

PROJECT TIMELINE

The summary of the assignment timeline detailed as below:

| ACTIVITY | FEB |  |  |  | MAC |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 |
| Project Preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Procurement Process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Appointment vendor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Facilitation Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Engagement /Workshop Session with selected State (1-6) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Workshop 7-9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proofread and Preparing Final Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| i. First draft |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ii. Progress Report 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| iii. Progress Report 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| iv. Progress Report 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| v. Interim report and info graphic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| v. Final Report and Final Info graphic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

The appointed associate is expected to provide the scope of work within the specified timeline. Payment will be made by MPC upon completion of the project activities.

The activity needs to be filled by the associate as stated below:

| NO. | ACTIVITIES | QUANTITY |
| --- | --- | --- |
| 1. | Facilitator and Moderator (9 Workshop Sessions): - 6 workshop sessions for selected states (1 day/workshop) - 3 workshops (2 days/workshop) (Requirement: minimum 3 personnel involve per session) | 6 days 6 days |
| 2. | Slide presentation for workshop session: - Workshop (selected state) - Workshop (engagement with MPC) - Finding (Final) | 3 |
| 3. | Interim Report (including infographic) | 1 |
| 4. | Editorial / Proofreading | 1 |
| 5. | Final Report | 1 |