KERTAS CADANGAN UNTUK PERTIMBANGAN

LEMBAGA PENGURUSAN MPC (BOM)

| TAJUK Keterangan: Tajuk Projek/ Cadangan | Update BOM for Q2/2022 of Electrical & Electronics Productivity Nexus (EEPN) Nexus Governing Committee: Focus Groups Workshops and Round Table Discussion (May - August 2022) |
| --- | --- |
| TARIKH/ GARIS MASA Keterangan: jadual mula dan akhir pelaksanaan projek/ cadangan | May - August 2022 (Please Refer Appendixes) |
| TUJUAN & LATAR BELAKANG Keterangan: tujuan dan penerangan ringkas mengenai projek | Organizing EEPN Nexus Governing Committee: Focus Groups Workshops and Round Table Discussion. Important to have a strong support from various parties to help ensure the continuity of implementation of EEPN initiatives as per the objectives outlined below: - To outline and discuss the strategic direction and support the EEPN activities; - To assist in the administration of EEPN and implement productivity initiatives; - To deliberate the implementation and monitor the progress of initiatives undertaken by EEPN; - To obtain guidance and input from professionals to increase productivity of the professional services sub -sector along the value chain; - To build relationships and opportunities for cooperation among industries, ministries and government agencies. Electrical & Electronics Productivity Nexus (EEPN) Coordinator - To assist the EEPN in consulting and monitoring projects approved by the Nexus Governing Committee - To support the Chairman in oversee the overall implementation of all initiatives under the respective Productivity Nexus; and - To support the Chairman in governing the nexus and implementing the productivity initiatives and activities |
| KAEDAH PELAKSANAAN Keterangan: kaedah yang perlu dilakukan bagi melaksanakan projek | Activities will be conducted both physically and virtually through online workshops and round table discussions; - Interview/Meetings with stakeholders - Round table discussions - Preparatory meetings for Webinars/Forums/Conference |
| STAKEHOLDERS/ PIHAK BERKEPENTINGAN Keterangan: pihak atau kumpulan yang menerima kesan positif mahupun negatif daripada projek yang dijalankan | E&E industry players; related Ministries and agencies |
| JANGKAAN HASIL/ OUTCOME Keterangan: apa yang MPC perlu capai/ faedah-faedah jangka pendek dan jangka panjang hasil dari intervensi projek/ cadangan | - Work plans from each Strategic Initiatives - Strategic Planning - Prepared slides for Chairman - Meeting minutes/notes of discussion |
| JANGKAAN OUTPUT Keterangan: output ketara dan tidak ketara yang dihasilkan daripada aktiviti projek/ cadangan. | - |
| KUMPULAN SASAR Keterangan: individu/ kumpulan yang menerima faedah daripada projek/ cadangan | Nexus Champions/ Secretariats/ industry Companies/ related Ministries and agencies |
| SUMBER BAJET/ KOS Keterangan: sumber bajet / jumlah kos yang terlibat. | MPB-EEPN; :; 79,050.00. Operational budget (OE); 14,880.00. Total; :; 93,930.00. Note: Details, please refer to Appendix 1 |
| HASIL (RM) - SEKIRANYA ADA Keterangan: pendapatan yang diterima daripada projek | - |
| SYOR Keterangan: permohonan yang diperlukan daripada Lembaga Pengurusan MPC | The approval of BOM is sought to approve the extension of time and allocation for the amount of RM89,130.00 from the MPB-EEPN budget to conduct the activities. |
| UNIT/ BAHAGIAN | Electrical & Electronics Productivity Nexus (EEPN) |

**Sila lampirkan maklumat-maklumat lain yang berkaitan sekiranya perlu.

(Contoh: Agenda program, pelan risiko, gambar rajah, lakaran pelan, senarai nama, dll.)

DISOKONG OLEH: NAMA PEGAWAI PENJAGA BAJET Jawatan: Nama Bajet: Tarikh: **Hanya untuk permohonan yang menggunakan Bajet Pembangunan dari Unit/Bahagian lain. Kolum ini boleh diabaikan sekiranya tidak berkaitan.

| DISEDIAKAN OLEH: Nurul Nadia Zainal Adnan Project Manager Tarikh: 29/3/2022 | DISEMAK OLEH: Lee Wan Wei Program Manager Date: 29/3/2022 | DISAHKAN OLEH: Dr. Mohamad Norjayadi Tamam Director Date: 6/4/2022 |
| --- | --- | --- |

APPENDIX 1

BUDGET / ESTIMATED COST

EEPN Nexus Coordinator Fees & Organizing EEPN Nexus Governing Committee via Focus Groups Workshops and Round Table Discussions

Followings are the estimated costs involved for EEPN Nexus Coordinator, organising the EEPN Nexus Governing Committee via Working Groups Workshops and Round Table Discussions, May - August 2022.

| No. | Item | Cost / Unit | Pax | Quantity |  | Total (RM) |
| --- | --- | --- | --- | --- | --- | --- |
| A. DEVELOPMENT BUDGET |  |  |  |  |  |  |
| 1) Nexus Coordinator |  |  |  |  |  |  |
|  | EEPN Nexus Coordinator includes accommodation and return flight or by car (km and toll) | 7,000.00 | 1 | 4 | months | 28,000.00 |
| 2) NGC Meeting/Strategic Planning Session |  |  |  |  |  |  |
| 1 | Meeting package | 250.00 | 35 | 1 | meeting | 8,750.00 |
| 2 | Travelling Expenses of EEPN Chairman | 1,500.00 | 1 | 2 | trips | 3,000.00 |
| 3) Round Table Discussion/ Focus Groups Workshops/ Webinar (Hybrid) |  |  |  |  |  |  |
| 1 | Networking F&B | 55.00 | 30 | - | pax | 1,650.00 |
| 2 | Facilitator | 250.00 | 4 | 2 | hours | 2,000.00 |
| 3 | Moderator | 250.00 | 3 | 3 | hours | 2,250.00 |
| 4 | Industry Experts | 400.00 | 4 | 36 | sessions | 14,400.00 |
| 5 | Report Writer (RM200/page) | 200.00 | 1 | 20 | pages | 4,000.00 |
| 6 | Proofreader/ editor | 150.00 | 1 | 20 | pages | 3,000.00 |
| 7 | Travelling Expenses of EEPN Chairman | 1,500.00 | 1 | 3 | trips | 4,500.00 |
| 8 | Press release | 1,000.00 | 4 | - | publication | 4,000.00 |
| 9 | Posters | 350.00 | 10 | - | publication | 3,500.00 |
| Total A |  |  |  |  |  | 79,050.00 |
| B. OPERATIONAL BUDGET |  |  |  |  |  |  |
| 1 | Travelling expenses of EEPN Secretariat | 800.00 | 2 | 6 | trips | 9,600.00 |
| 2 | Accommodation | 220.00 | 2 | 12 | nights | 5,280.00 |
| Total B |  |  |  |  |  | 14,880.00 |
| Grand Total (A + B) |  |  |  |  |  | 93,930.00 |