KERTAS CADANGAN UNTUK PERTIMBANGAN

LEMBAGA PENGURUSAN MPC (BOM)

| TAJUK Keterangan: Tajuk Projek/ Cadangan | Digital contents for E&E 50th Years Anniversary |
| --- | --- |
| TARIKH/ GARIS MASA Keterangan: jadual mula dan akhir pelaksanaan projek/ cadangan | April – July 2022 (Please Refer Appendix 1) |
| TUJUAN & LATAR BELAKANG Keterangan: tujuan dan penerangan ringkas mengenai projek | The Electrical and Electronics Productivity Nexus (EEPN) was established under the Malaysia Productivity Blueprint (MPB) with the theme on “Driving Productivity of the Nation”. Digital mapping is created to promote Malaysia E&E industry to the world. It will help in the analysis and understanding density of the E&E industry and its supply chain. |
| KAEDAH PELAKSANAAN Keterangan: kaedah yang perlu dilakukan bagi melaksanakan projek | - To gather information of E&E industry and create digital map of locations and subsectors. - To create a map similar to the map of Silicon Valley - To celebrate 50 Years of Excellence of Malaysia E&E Industry – The 50 Years That Make The Difference |
| STAKEHOLDERS/ PIHAK BERKEPENTINGAN Keterangan: pihak atau kumpulan yang menerima kesan positif mahupun negatif daripada projek yang dijalankan | - Captains of E&E industry, MNCs, LLCs and SMEs - EEPN Governing Committee - Related ministries and agencies esp. EPU, MITI and its agencies esp.; MIDA, MATRADE & SME Corp. |
| JANGKAAN HASIL/ OUTCOME Keterangan: apa yang MPC perlu capai/ faedah-faedah jangka pendek dan jangka panjang hasil dari intervensi projek/ cadangan | - To promote Malaysia E&E industry to the world. - To develop Bubble Analysis Digital Map of the E&E Industry |
| JANGKAAN OUTPUT Keterangan: output ketara dan tidak ketara yang dihasilkan daripada aktiviti projek/ cadangan. | 1) Digital mapping (Malaysia & Penang) 2) Video |
| KUMPULAN SASAR Keterangan: individu/ kumpulan yang menerima faedah daripada projek/ cadangan | - MSIA members & E&E Companies (MNCs, LLCs and SMEs - EEPN Governing Committee - Related ministries and agencies |
| SUMBER BAJET/ KOS Keterangan: sumber bajet / jumlah kos yang terlibat. | SPC : RM100,000.00 (Please Refer Appendix 1) |
| HASIL (RM) - SEKIRANYA ADA Keterangan: pendapatan yang diterima daripada projek | Nil |
| SYOR Keterangan: permohonan yang diperlukan daripada Lembaga Pengurusan MPC |  |
| UNIT/ BAHAGIAN | Electrical & Electronics Productivity Nexus (EEPN) |

**Sila lampirkan maklumat-maklumat lain yang berkaitan sekiranya perlu.

(Contoh: Agenda program, pelan risiko, gambar rajah, lakaran pelan, senarai nama, dll.)

DISOKONG OLEH: NAMA PEGAWAI PENJAGA BAJET Jawatan: Nama Bajet: Tarikh: **Hanya untuk permohonan yang menggunakan Bajet Pembangunan dari Unit/Bahagian lain. Kolum ini boleh diabaikan sekiranya tidak berkaitan.

| DISEDIAKAN OLEH: Nurul Nadia Zainal Adnan Project Manager Tarikh: 6/4/2022 | DISEMAK OLEH: Lee Wan Wei Programme Manager Date: 6/4/2022 | DISAHKAN OLEH: Dr Mohamad Norjayadi Tamam Director Date: 7/4/2022 |
| --- | --- | --- |

APPENDIX 1

# 1.0 Project Timeline for Video & Digital Contents (April - July)

|  | Activity | Apr | May | Jun | Jul |
| --- | --- | --- | --- | --- | --- |
| 1 | Procurement process - Request for Quote (RFQ) - Appointment of vendor |  |  |  |  |
| 2 | Start project - Mapping of Malaysia & Penang (silicon valley of east) 50th E&E Anniversary video Pre-production: Project kick-off meeting, recce, detailed planning, establishing contacts. ( Shooting plan and schedule |  |  |  |  |
| 3 | Bubble Analysis Digital Map - analysis on the company’s revenue or export value 50th E&E Anniversary video Production: 8 days shooting (Shooting report) |  |  |  |  |
| 4 | Compilation of Digital Mapping (final output) 50th E&E Anniversary video Post-production (Final Video) |  |  |  |  |

# 2.0 Estimated cost

The overall cost of the project is shown in the table below:

| No. | Item | Cost (RM) | Quantity | Budget | Total (RM) |
| --- | --- | --- | --- | --- | --- |
| 1. | Malaysia and Penang E&E maps & - Similar to U.S. Silicon Valley map. - The total number of companies to be reflected on both the maps collectively shall be between 200-300. - Add significant landmarks e.g. Petronas Twin Towers, Putrajaya, Parliament House, Penang Bridge, Komtar, Penang Hill, etc. in the map. - Include E&E 50th anniversary logo by MSIA Bubble Analysis Digital Map - Same details as the above (where applicable). - Option to select different electronic sectors such as Semiconductor, EMS, LED, Solar, automation etc. - Option to select analysis type; the size of the bubbles shall reflect the company’s revenue or export value. - Sample: https://www.siliconvalleymap.org/#about Digital version of Penang map & Malaysia map - Interactive map with mouse over. Sample: https://siliconmaps.com/silicon-valley-map/ |  | 1 |  | 50,000.00 |
| 2. | 50th E&E Anniversary video PRE-PRODUCTION - Concept development - Research - Recce / location scouting - Detailed planning - Scriptwriting PRODUCTION - 8-days shooting (8 - 10 hours / day) in Penang & Klang Valley - Camera: Panasonic Varicam LT 4K Super 35 Digital Cinema Camera - Grip & gear - Special lens for conceptual angles - Conceptual lightings - Resources:1 Producer/Director (Senior), 1 Director of Photography, 1 Videographer, 1 Gaffer, 1 Soundman, 2 Production Assistants - Travelling and accommodation - shooting outside of Penang (5 days) POST-PRODUCTION - Video editing, motion graphics, open titles, lower thirds, color grading Audio post: - Voice over: English (1 talent / per session / per video) - Licensed music (special editing) - Audio enhancement & audio mixing |  |  |  | 50,000.00 |
| Total Cost (RM) |  |  |  |  | 100,000.00 |