PAPER FOR APPROVAL

MPC BOARD OF MANAGEMENT (BOM)

| TITLE | Accelerate adoption of Industry 4.0 technology through Artificial Intelligence for SMEs (AI4S) Enhanced Programme – Continuous project. |
| --- | --- |
| DATE / DURATION | May – August 2022 |
| OBJECTIVES AND BACKGROUND | The Artificial Intelligence for SMEs (AI4S) enhanced programme established with the collaboration between Malaysia Productivity Corporation (MPC), Malaysian Investment Development Authority (MIDA) and Intel Malaysia has been successfully launched 27 Oct 2021. In 2022, the team planned to upskill 80 SMEs which aimed to equipped them with sufficient knowledge to be able to use FPGA (Field Programmable Gate Array) to solve AI problem and enhanced the performance of SMEs’ AI solutions. |
| METHODS OF IMPLEMENTATION | Activities will be conducted virtually through online workshops. |
| STAKEHOLDERS | - Working Committee: MIDA, INTEL, MPC - Beneficiary: 100 SMEs |
| EXPECTED OUTCOME | The output expected from the participants is to developed and established Proof of Concept (PoC) project which help SMEs to use the FPGA card to boost the performance of deep learning in the current pilot project that they are working on. |
| EXPECTED OUPUT | - Training workshop - Workshop/Program reports - Proof-of-concept projects |
| TARGET GROUP | Malaysian companies from the manufacturing sectors such as chemical & chemical products, machinery& equipment, electrical & electronic products, pharmaceuticals, medical devices & solutions, building technology & lifestyle, wood-based, food technology, engineering support industry (ESI) and as well as the services sector such as R&D services & autonomous vehicle, solution provider, system integrators, drone services, green technology & renewable energy and electronics manufacturing services (EMS) identified by MIDA |
| BUDGET / ESTIMATED COST | SPC : RM63,000 (Please Refer Appendix 1) |
| INCOME (RM) – IF ANY | - |
| RECOMMENDATION | The approval of BOM is sought to approve the budget of RM63,000.00 to utilize the MPB-EEPN for accelerating adoption of Industry 4.0 technology [Artificial Intelligence for SMEs (AI4S) Enhanced Programme], May - August 2022. |
| UNIT / DIVISION | Electrical & Electronics Productivity Nexus (EEPN), Delivery Management Office (DMO) |

**Please attach other relevant information if necessary.

(Examples: Program agenda, cost details, risk plan, diagrams, plan sketches, name lists, Gantt charts, etc.)

Only for applications that use Development Budget from other Units/Divisions. This column can be ignored if it is not relevant.

SUPPORTED BY: NAME OF OFFICER IN CHARGE OF THE DEVELOPMENT BUDGET Position: Budget Name: Date:

| PREPARED BY: Nurul Nadia Zainal Adnan Programme Manager Date: 13/4/2022 | REVIEWED BY: Lee Wan Wei Manager Date: 13/4/2022 | APPROVED BY: Dr. Mohamad Norjayadi Tamam Director Date: 14/4/2022 |
| --- | --- | --- |

APPENDIX 1

BUDGET / ESTIMATED COST

Accelerate adoption of Industry 4.0 technology [Artificial Intelligence for SMEs (AI4S) Enhanced Programme]

Followings are the estimated costs involved for accelerate adoption of Industry 4.0 technology [Artificial Intelligence for SMEs (AI4S) Enhanced Programme].

# Estimated Total Cost (Jan – Oct 2022)

# The table below shows the overall budget for the programme

| # | Activity | Cost per unit (RM) | Total (RM) |
| --- | --- | --- | --- |
| 1. | Food Voucher For participants, secretariat, and trainers) Participants: 100 companies (2 pax per company | RM15 x 20 pax x 2 half days x 5 session | 3,000.00 |
| 2. | Lead Facilitator (RM250/hour) + RM500/programme | RM3,000 x 10 months | 30,000.00 |
| 3. | Facilitator (RM250/hour) | RM2,500 x 10 months | 25,000.00 |
| 4. | Printing and Publication - Finalising before and after of proof-of-concept Report for participating companies - Writer x 20 pages - Design Charges, Layout and Printing - Idea, Conceptual & Art Direction - Colour and Photo Manipulation - Design of infographics - Final Artwork in PDF format for online publication, printing and raw file - Printing content, front and back cover (20 copies) - Sharing on findings/digital video content | RM20,000 RM8,000 RM10,000 | 38,000.00 |
| TOTAL |  |  | 96,000.00 |

# Estimated April - August 2021

# The table below shows the budget for next 4 months for the programme

| # | Activity | Cost per unit (RM) | Total (RM) | Budget |
| --- | --- | --- | --- | --- |
| 1. | Food Voucher For participants, secretariat, and trainers) Participants: 100 companies (2 pax per company | RM15 x 20 pax x 2 half days x 5 session | 3,000.00 | SPC 2.0 |
| 2. | Lead Facilitator (RM250/hour) + RM500/programme | RM3,000 x 4 months | 12,000.00 | SPC 2.0 |
| 3. | Facilitator (RM250/hour) | RM2,500 x 4 months | 10,000.00 | SPC 2.0 |
| 4. | Printing and Publication E-Book (Deliverables) Page: 110 pages Ebook Size: 21cm x 21cm (Custom Size) - Artwork and Design for Cover Page - Artwork and Design for Layout of content - Stock photo / images - Format: - PDF for online publication included: - Spread view for E-Book - Page bookmarks - Clickable Link - PDF for printing (hi-resolution) - Raw File (PDF/PSD/Ai/InD/Image) - Pendrive Printing (Deliverables) – 200 copies - Type: Booklet - Size: 21cm x 21cm (Custom Size) Cover: Matt Lam Spot UV (Art260gsm) Finishing: Perfect Binding - Status: Normal Print Content: 110pages (Art paper 128gsm) 2 sides Proofread/ editor (RM150/page) x 110 | 9,010.00 9,460.00 16,500.00 | 34,970.00 | SPC 2.0 |
| TOTAL |  |  | 59,970.00 |  |