KERTAS CADANGAN UNTUK PERTIMBANGAN

LEMBAGA PENGURUSAN MPC (BOM)

| TAJUK Keterangan: Tajuk Projek/ Cadangan | STRATEGIC COMMUNICATION ON PEMUDAH |
| --- | --- |
| TARIKH/ GARIS MASA Keterangan: Jadual mula dan akhir pelaksanaan projek/ cadangan | January - Dec 2023 (Lampiran 1) |
| TUJUAN & LATAR BELAKANG Keterangan: Tujuan dan penerangan ringkas mengenai projek | PEMUDAH is working closely with Government and Private Sector to help businesses survive through pandemic struggles and to help accelerate national economic recovery by resolving regulatory issues and increasing international competitiveness, efficiency, productivity, innovation, and sustainability PEMUDAH will facilitate growth in the sectors prioritised under RMKe-12 by harmonizing regulatory requirements with business needs to start, expand, or upgrade their businesses with ease at minimum costs and to continue to operate seamlessly. Objective: To promote better understanding and create awareness on PEMUDAH initiatives towards improving and facilitating a more conducive business environment. |
| sJUSTIFIKASI Keterangan: Penjelasan yang menyokong kepada pelaksanaan projek/ cadangan | PEMUDAH is a strategic platform to discuss and review existing regulations (regulatory policy and delivery) in terms of processes, procedures, legislation, and human resources and to propose new policies for improvements. This will contribute to the improvement of Malaysia’s competitiveness and productivity. |
| KAEDAH PELAKSANAAN Keterangan: Kaedah yang perlu dilakukan bagi melaksanakan projek | - Engagement with between regualtors and industries; - Appointment of experts in related subject matters; - Preparing reports |
| STAKEHOLDERS/ PIHAK BERKEPENTINGAN Keterangan: Pihak atau kumpulan yang menerima kesan positif mahupun negatif daripada projek yang dijalankan | Ministries, Agencies, Department, Local Authorities, Business Associations, and Public. |
| JANGKAAN HASIL/ OUTCOME Keterangan: Apa yang MPC perlu capai/ faedah-faedah jangka pendek dan jangka panjang hasil dari intervensi projek/ cadangan | - Improvement in Malaysia’s business climate, efficiency, and competitiveness. - Regulatory reform initiatives to improve ease of doing business in Malaysia; and - Enhanced national competitiveness and productivity. |
| JANGKAAN OUTPUT Keterangan:Output ketara dan tidak ketara yang dihasilkan daripada aktiviti projek/ cadangan. | - Engagement reports - Press release on PEMUDAH initiatives - PEMUDAH Annual report 2023 - PEMUDAH Forum 2023 - Onboarding sessions with a business associations. |
| KUMPULAN SASAR Keterangan: Individu/ kumpulan yang menerima faedah daripada projek/ cadangan | 1. Ministries and agencies 2. Industries 3. Public |
| SUMBER BAJET/ KOS Keterangan: Sumber bajet / jumlah kos yang terlibat. | DE (Budget FORE 2023) : RM 257,800.00 OE 2023 : RM 63,000.00 |
| HASIL (RM) - SEKIRANYA ADA Keterangan: Pendapatan yang diterima daripada projek | NA |
| SYOR Keterangan: Keputusan yang diperlukan daripada Lembaga Pengurusan MPC | The approval of the Board of Management (BOM) is sought for the implementation of Forging a Robust Ecosystem programme with utilising the DE budget of RMK12 Forging a Robust Ecosystem and OE budget 2023 amounting RM257,800.00 and RM63,000.00 respectively |
| UNIT/ BAHAGIAN | NCS/PCD |

**Sila lampirkan maklumat-maklumat lain yang berkaitan sekiranya perlu.

(Contoh: Agenda program, perincian kos, pelan risiko, gambar rajah, lakaran pelan, senarai nama, carta Gantt, dll.)

Hanya untuk permohonan yang menggunakan Bajet Pembangunan dari Unit/Bahagian lain. Kolum ini boleh diabaikan sekiranya tidak berkaitan.

DISOKONG OLEH: NAMA PEGAWAI PENJAGA BAJET PEMBANGUNAN Jawatan: Nama Bajet: Tarikh:

| **Wajib diisi | **Wajib diisi | Permohonan memadai disemak sehingga peringkat Penyelia. Kolum ini boleh diabaikan sekiranya tidak berkaitan |
| --- | --- | --- |
| DISEDIAKAN OLEH: NAMA PEMOHON Darul Adizul Ishak Pengurus Tarikh: 24 Jan 2023 | DISEMAK OLEH: NAMA PENYELIA Azlin Mohd Alias Pengurus Kanan Tarikh: 24 Jan 2023 | DISAHKAN OLEH: NAMA PENGARAH Mohammed Alamin Rehan Pengarah Tarikh: 24 Jan 2023 |

Attachment 1 – Cost Details

|  | Type of Payment | Cost per Unit (RM)* | No. of Unit (man-hour/ pax) | Total Cost (RM) |  |
| --- | --- | --- | --- | --- | --- |
| - DEVELOPMENT BUDGET (FORE) |  |  |  |  |  |  |
| A | MPC ASSOCIATES |  |  |  |  |
|  | Rapporteur | 100/page | 300 pages | 30,000 |  |
|  | Writer (speeches, NJM) | 200/page | 285 pages | 57,000 |  |
|  | Input for media | 1,000/article | 15 articles | 15,000 |  |
|  | Moderator | 250 / hour | 2 hours x 1 person | 500.00 |  |
|  | Video/ digital content/background | 5,000 / unit | 2 units | 10,000.00 |  |
|  | Subject Matter Experts (SMEs) | 400/hour | 10 hours | 4,000.00 |  |
|  | Total (a) |  |  | 116,500.00 |  |
| B | PROGRAM PACKAGES |  |  |  |  |
|  | Half Day Seminar Package/ Meeting Package [Incl. of F&B, WiFi, flip charts, meal voucher (online programme), etc] | 160/pax | 150 pax | 24,000.00 |  |
|  | Flight Ticket | 1,000 / pax | 1 pax | 1,000.00 |  |
|  | Accommodation | 500 / pax | 10 pax | 5,000.00 |  |
|  | Total (b) |  |  | 30,000.00 |  |
| C | COMMUNICATION PLAN |  |  |  |  |
|  | Printing PEMUDAH meeting documents | 290/pc | 10 pcs x 11 meetings | 34,800.00 |
|  | Writing and Editorial | 20,000/unit | 1 unit | 20,000.00 |
|  | Printing PEMUDAH Report 2022 | 500/unit | 40 pcs | 20,000.00 |
|  | Renewal license PEMUDAH portal | 1,000/unit | 1 unit | 1,000.00 |
|  | Recording services multi camera production | 20,000/unit | 1 unit | 20,000.00 |
|  | Honorarium: Batik | 500 / pc | 10 pcs | 5,000.00 |
|  | Certificate of Appreciation | 50 / pc | 10 pcs | 500.00 |
|  | Promotional items (bunting, banner, poster, booster etc (online) | 5,000 / unit | 2 units | 10,000.00 |
|  | Total (c) |  |  | 111,300.00 |
|  | TOTAL DEVELOPMENT BUDGET (FORE) (A + B + C) |  |  | 257,800.00 |  |
| 2. OPERATIONAL BUDGET |  |  |  |  |  |  |
| D | EXPENSES FOR MPC OFFICERS |  |  |  |  |
| 1. | Claims (Mileage, meals, toll taxi/grab). | 2,000 / pax** | 20 pax | 40,000.00 |  |
| E | PROGRAM PACKAGES |  |  |  |  |
|  | Dinner Package (for PEMUDAH Appreciation Dinner) | 200 / pax | 100pax | 20,000.00 |  |
|  | Performance (Band) | 3,000 / unit | 1 unit | 3,000.00 |  |
|  | TOTAL OPERATIONAL BUDGET |  |  | 63,000.00 |  |

Notes:

- Estimated max. cost per unit under PCT’s guidelines (JPPK)

- The cost is subject to modification to suit with the program either physical or

virtual **

Appendix 1 – PEMUDAH Engagement

| No | Item | Cost per Unit RM | Unit | Total cost RM |
| --- | --- | --- | --- | --- |
|  | Rapporteur (Jurulapor) - PEMUDAH meeting (11 meetings) - PEMUDAH Private Sector meeting (11 meetings) | 100.00 / page | 10 pages x 22 times | 22,000.00 |
|  | Writer for Speeches: - Co-chair PEMUDAH (Private) (22 speeches) - Co-chair PEMUDAH (Government) (11 speeches) - Co-chair PEMUDAH (Government) (11 speeches) | 200.00/ page | 44 speeches x 4 pages | 35,200.00 |
|  | Report writer on Nota Jemaah Menteri for PEMUDAH meeting (11 meetings) | 200.00/ page | 5 pages x 11 meetings | 11,000.00 |
|  | Writing media release/ article | 1,000.00 / article | 11 articles | 11,000.00 |
|  | Printing PEMUDAH meeting documents | 290.00 / documents | 10 documents x 11 meetings | 34,800.00 |
|  | Half-day seminar package - PPS No.1/2023 meeting | 180 / pax | 50 pax x 1 meeting | 9,000.00 |
|  | TOTAL |  |  | 123,000.00 |

PEMUDAH: DATE OF MEETING 2023

| NO. OF MEETING | DATE | TIME | SECRETARIAT |
| --- | --- | --- | --- |
| 1/2023 | 16 February 2023 (Thursday) | 9.30 a.m – 11.30 a.m | T1 |
| 2/2023 | 23 March 2023 (Thursday) | 9.30 a.m – 11.30 a.m | T4 |
| 3/2023 | 13 April 2023 (Thursday) | 9.30 a.m – 11.30 a.m | T2 |
| 4/2023 | 25 May 2023 (Thursday) | 9.00 a.m – 11.30 a.m | T1 |
| 5/2023 | 22 June 2023 (Thursday) | 9.00 a.m – 11.30 a.m | T3 |
| 6/2023 | 20 July 2023 (Thursday) | 9.30 a.m – 11.30 a.m | T4 |
| 7/2023 | 17August 2023 (Thursday) | 9.30 a.m – 11.30 a.m | T2 |
| 8/2023 | 21 September 2023 (Thursday) | 9.30 a.m – 11.30 a.m | T1 |
| 9/2023 | 19 October 2023 (Thursday) | 9.30 a.m – 11.30 a.m | T3 |
| 10/2023 | 23 November 2023 (Thursday) | 9.30 a.m – 11.30 a.m | T4 |
| 11/2023 | 21 December 2023 (Thursday) | 9.30 a.m – 11.30 a.m | T2 |

PEMUDAH PRIVATE SECTOR (PPS): DATE OF MEETING 2023

| NO. OF MEETING | DATE | TIME | SECRETARIAT |
| --- | --- | --- | --- |
| 1/2022 | 2 February 2023 (Thursday) | 10.00 a.m – 12.00 p.m | T1 |
| 2/2022 | 2 March 2023 (Thursday) | 10.00 a.m – 12.00 p.m | T3 |
| 3/2022 | 6 April 2023 (Thursday) | 10.00 a.m – 12.00 p.m | T4 |
| 4/2022 | 11 May 2023 (Wednesday) | 10.00 a.m – 12.00 p.m | T2 |
| 5/2022 | 8 June 2023 (Thursday) | 10.00 a.m – 12.00 p.m | T1 |
| 6/2022 | 6 July 2023 (Thursday) | 10.00 a.m – 12.00 p.m | T3 |
| 7/2022 | 3 August 2023 (Thursday) | 10.00 a.m – 12.00 p.m | T4 |
| 8/2022 | 7 September 2023 (Thursday) | 10.00 a.m – 12.00 p.m | T2 |
| 9/2022 | 5 October 2023 (Thursday) | 10.00 a.m – 12.00 p.m | T1 |
| 10/2022 | 2 November 2023 (Thursday) | 10.00 a.m – 12.00 p.m | T3 |
| 11/2022 | 8 December 2023 (Friday) | 9.30 a.m – 11.30 a.m | T4 |

Appendix 2 – PEMUDAH Annual Report 2022

| No | Item | Cost per Unit RM | Unit | Total cost |
| --- | --- | --- | --- | --- |
| 1 | Writing and Editorial | 20,000 / unit | 1 | 20,000.00 |
| 2 | Designing, Layout and Printing | 500 / unit | 40 | 20,000.00 |
| 3 | Writing media release/ article | 1,000 / article | 1 article | 1,000.00 |
|  | TOTAL |  |  | 41,000.00 |

PROPOSED TIMELINE

| BIL. | ACTIVITIES | FEB | MAR | APRIL | MEI | JUN |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Administration |  |  |  |  |  |
| 2. | Preparation Table of Content |  |  |  |  |  |
| 3. | Gathering inputs on Achievement for 2022 from all TWG Secretariats |  |  |  |  |  |
| 4. | 1st Draft of the PEMUDAH Report 2022 |  |  |  |  |  |
| 5. | MPC Management Feedback |  |  |  |  |  |
| 6. | 2nd Draft of the PEMUDAH Report 2022 |  |  |  |  |  |
| 7. | Final Draft of the PEMUDAH Report 2022 |  |  |  |  |  |
| 8. | Printing of PEMUDAH Report 2022 |  |  |  |  |  |
| 9. | Launching of the PEMUDAH Report 2022 |  |  |  |  |  |

Appendix 3 – PEMUDAH Appreciation Dinner 2023

| No | Item | Cost per Unit RM | Unit | Total cost |
| --- | --- | --- | --- | --- |
| 1 | Dinner Package | 200.00 / pax | 100 | 20,000.00 |
| 2 | Accommodation | 500.00 / pax | 10 | 5,000.00 |
| 3 | Certificate of Appreciation | 50.00 / pc | 10 | 500.00 |
| 4 | Performance (Band) | 3,000.00 | 1 | 3,000.00 |
| 5 | Writer for Speeches: - Speech for 4 Speakers | 100.00 / page | 5 pages x 4 sets | 4,000.00 |
| 6 | Honorarium: - Batik | 500.00 / pc | 10 | 5,000.00 |
|  | TOTAL |  |  | 33,500.00 |

Appendix 4 – PEMUDAH Forum 2023

| No | Item | Cost per Unit RM | Unit | Total cost |
| --- | --- | --- | --- | --- |
|  | Panelist (5 persons) | 400 / hour | 2 hours x 5 persons | 4,000.00 |
|  | Moderator (1 person) | 250 / hour | 2 hours x 1 person | 500.00 |
|  | Half- day seminar package/meeting package (External participants > 60%) incl plenary meeting room, refreshments, business lunch, internet access, lcd projector & screen, wireless microphone, flipchart, whiteboard | 160 / pax | 100 pax x 1 session | 16,000.00 |
|  | Video/ digital content/background | 5,000 / unit | 2 units | 10,000.00 |
|  | Writing media release/ article | 1,000 / article | 2 articles | 2,000.00 |
|  | Rapporteur | 100 / page | 10 pages | 1,000.00 |
|  | Promotional items (bunting, banner, poster, booster etc (online) | 5,000 / unit | 2 units | 10,000.00 |
|  | Speeches | 200 / page | 3 speeches x 4 pages | 2,400.00 |
|  | Recording services multi camera production (mcp);including video camera & equipment, recording & platform for online broadcast, producer, production crew, coordinator, moderator (celebrity) | 20,000 / unit | 1 unit | 20,000.00 |
|  | TOTAL |  |  | 65,900.00 |