KERTAS CADANGAN UNTUK PERTIMBANGAN

LEMBAGA PENGURUSAN MPC (BOM)

| TAJUK Keterangan: Tajuk Projek/ Cadangan | The Publication of Malaysia Behavioural Insights (BI) Guideline |
| --- | --- |
| TARIKH/ GARIS MASA Keterangan: Jadual mula dan akhir pelaksanaan projek/ cadangan | January 2022 – May 2022 |
| TUJUAN & LATAR BELAKANG Keterangan: Tujuan dan penerangan ringkas mengenai projek | The objectives of the Malaysia BI Guideline are: - To serve as a guide in applying behavioural insights to public policy from the beginning to the end of the policy cycle; - To serve as a repository of best practices, proof of concepts and methodological standards for behavioural insights practitioners and policymakers; and - To provide general principles for the ethical application of BI and guidelines where ethical concerns might be raised for specific issues. |
| JUSTIFIKASI Keterangan: Penjelasan yang menyokong kepada pelaksanaan projek/ cadangan | MPC has been mandated by the government to undertake BI programs and initiatives for Malaysia year 2020 onwards. Publishing a BI Guideline that best suits the nation’s culture that includes individual, environment, and social factors especially in every stage of the policy cycle is essential in order to provide better quality and more effective regulations |
| KAEDAH PELAKSANAAN Keterangan: Kaedah yang perlu dilakukan bagi melaksanakan projek | - To assess Malaysia’s current design and implementation of public policy; - To conduct research of existing behavioural theories, methodologies, public policy issues and challenges; and - To establish a BI Guideline that includes designing solutions to ensure that policies reflect real needs and behaviours for greater impact and effectiveness. |
| STAKEHOLDERS/ PIHAK BERKEPENTINGAN Keterangan: Pihak atau kumpulan yang menerima kesan positif mahupun negatif daripada projek yang dijalankan | - Ministries - Agencies - Pihak Berkuasa Tempatan (PBT) - Business Association - Business Community |
| JANGKAAN HASIL/ OUTCOME Keterangan: Apa yang MPC perlu capai/ faedah-faedah jangka pendek dan jangka panjang hasil dari intervensi projek/ cadangan | - Integrated BI Guideline to be used at national level. - Well-informed regulators on matters relating to BI on designing public policy |
| JANGKAAN OUTPUT Keterangan:Output ketara dan tidak ketara yang dihasilkan daripada aktiviti projek/ cadangan. | - 1 BI Guideline for Ministries - 4 BI Guidelines Project for selected Ministries and agencies |
| KUMPULAN SASAR Keterangan: Individu/ kumpulan yang menerima faedah daripada projek/ cadangan | - Ministries - Agencies - Pihak Berkuasa Tempatan (PBT) - Business Association |
| SUMBER BAJET/ KOS Keterangan: Sumber bajet / jumlah kos yang terlibat. | RM350,000.00 (Bajet RMK-12 BEHAVIOURAL INSIGHTS (BI)) (As in Appendix) |
| HASIL (RM) - SEKIRANYA ADA Keterangan: Pendapatan yang diterima daripada projek | N/A |
| SYOR Keterangan: Keputusan yang diperlukan daripada Lembaga Pengurusan MPC | Apply for BOM approval for the development of the Behavioral Insights Guidelines |
| UNIT/ BAHAGIAN | Seksyen Daya Saing Negara/ PCD |

**Sila lampirkan maklumat-maklumat lain yang berkaitan sekiranya perlu.

(Contoh: Agenda program, perincian kos, pelan risiko, gambar rajah, lakaran pelan, senarai nama, carta Gantt, dll.)

Project Phase

| PHASE | ACTIVITY |
| --- | --- |
| Development & Monitor (5 months) | Development of BI Guideline tailored specifically for the ministries and monitoring of intervention projects. |
| Advocacy (2 months) | Promotional activities such as media release, webinars, sharing sessions, videos, posters etc, including content development. |
| Advisory (3 months) | - Projects identified in Ministries - Training to ministries as a preparation before embarking on the projects |
| Coordination (4 months) | Embark on projects with selected ministries. |

Project Timeline

| PHASE | JANUARY | FEBRUARY | MARCH | APRIL | MAY |
| --- | --- | --- | --- | --- | --- |
| Development & Monitor (5 months) |  |  |  |  |  |
| Advocacy (2 months) |  |  |  |  |  |
| Advisory (3 months) |  |  |  |  |  |
| Coordination (4 months) |  |  |  |  |  |

Estimated Cost

| NO. | PHASE | ITEM | ESTIMATED COST (RM) | TOTAL (RM) |
| --- | --- | --- | --- | --- |
| 1. | Development & Monitor | Hiring of subject matter experts (SME) to develop Guideline RM30,000 x 2 SMEs | 60,000.00 | 88,000.00 |
|  |  | Hiring of subject matter experts (SME) to monitor and test BI Guideline RM 14000 x 2 SMEs | 28,000.00 |  |
| 2. | Advocacy | Media Statement RM1,000 x 4 media statements | 4,000.00 | 70,000.00 |
|  |  | Sharing session - Fee for Speaker RM300 x 8 hours = RM2400 - Moderator RM250 x 8 hours = RM2000 - Coordinator RM1,000 x 8 sessions = RM8000 - Rapporteur RM100 x 80 pages = RM8000 - Facilitator RM250 x 8 hours = RM2000 | 22,400.00 |  |
|  |  | Video and promotional items - Interactive video, corporate, public service announcement RM6,000 x 4 | 24,000.00 |  |
|  |  | Online platform, digital content, digital publication, and tools (Murals, posters, ebook, database, etc) | 19,600.00 |  |
| 3. | Advisory | Hiring of SMEs / Trainer / Facilitators to share knowledge and experience through training and reporting on National BI Guideline. Conduct of intervention projects/pilot studies with selected ministries/agencies PBT’s or Business Association. (RM 20,000 x 4 Advisory Sessions) | 80,000.00 | 80,000.00 |
| 4. | Coordination | Residential Workshop (RM450 x 20pax x 8 sessions) | 72,000.00 | 112,000.00 |
|  |  | Engagements with ministries (RM5,000 x 8 sessions) | 40,000.00 |  |
| TOTAL |  |  |  | 350,000.00 |

Hanya untuk permohonan yang menggunakan Bajet Pembangunan dari Unit/Bahagian lain. Kolum ini boleh diabaikan sekiranya tidak berkaitan.

DISOKONG OLEH: NAMA PEGAWAI PENJAGA BAJET PEMBANGUNAN Jawatan: Nama Bajet: Tarikh:

| **Wajib diisi | **Wajib diisi | Permohonan memadai disemak sehingga peringkat Penyelia. Kolum ini boleh diabaikan sekiranya tidak berkaitan |
| --- | --- | --- |
| DISEDIAKAN OLEH: SHANTHINI TAMADORAM Penolong Pengurus 21 Januari 2022 | DISEMAK OLEH: NORHASIMAH IBRAHIM Timbalan Pengarah 21 Januari 2022 | DISAHKAN OLEH: WAN FAZLIN NADIA WAN OSMAN Pengarah 21 Januari 2022 |