## Slide 1
MILESTONE FOR WORLD COMPETITIVENESS YEARBOOK (WCY) ACTIVITIES
Actual
Plan
Activities​ / Time | 2023 |  |  | 2023 |  |  |  |  |  |  |  | 
Activities​ | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC
1. NCS Meeting with TKP | 18 |  |  |  |  |  |  |  |  |  |  | 
2. Email from World Competitiveness Center and Partner Institute on Translation Survey | 25 |  |  |  |  |  |  |  |  |  |  | 
3. BOM Paper and Approval Procedures |  | 2 |  |  |  |  |  |  |  |  |  | 
4. Prepare the list of AIPG Members and Potential Survey Respondents |  | 10 |  |  |  |  |  |  |  |  |  | 
5. WCC sends list of data to be completed with the most recent information from national statistics (HARD DATA) |  | 17 |  |  |  |  |  |  |  |  |  | 
6. WCC sends the link to the online business executives' questionnaire, for all languages |  | 17 |  |  |  |  |  |  |  |  |  | 
7. Meeting with IAPG Members (Mr. Wong Presentation on Data Definition to IAPG Members) |  | 23 |  |  |  |  |  |  |  |  |  | 
8. WCC and Partners carry out a mailing (e-mail with link to the online questionnaire) to business executives in top or middle management, representative of all sectors of the economy, according to WCC survey guidelines |  | 28 |  |  |  |  |  |  |  |  |  | 
9. IMD WCY Survey (Workshop 1) (Online/Physical) |  |  | 2 |  |  |  |  |  |  |  |  | 
10. Hard Data Submission to MPC from IAPG members (Deadline) |  |  | 17 |  |  |  |  |  |  |  |  | 
11. Checking and Key in of the Submitted Hard Data |  |  | 23 |  |  |  |  |  |  |  |  | 
11. Partners send back the completed list of statistical data. (HARD DATA SUBMISSION TO IMD) |  |  | 31 |  |  |  |  |  |  |  |  | 
12. IMD WCY Survey (Workshop 2) (Online/Physical) |  |  |  | 11 |  |  |  |  |  |  |  | 
13. Submission of Key Challenges from Malaysia and Partner’s details update |  |  |  | 19 |  |  |  |  |  |  |  | 
14. The deadline for survey responding online (END OF SURVEY) |  |  |  | 30 |  |  |  |  |  |  |  | 
MPC’s Task

## Slide 2
MILESTONE FOR WORLD COMPETITIVENESS YEARBOOK (WCY) ACTIVITIES
Actual
Plan
Activities​ / Time | 2023 |  |  | 2023 |  |  |  |  |  |  |  | 
Activities​ | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC
15. Data checking and processing (cut-off date) HARD DATA (WCC will send the data set for their country to all Partner Institutes, including the criteria time series. At this point Partners can suggest updates, but only for major differences in data.) |  |  |  |  | 3 |  |  |  |  |  |  | 
16. WCC merges and analyzes all data according to the IMD World Competitiveness Yearbook methodology. Writing of analysis |  |  |  |  | 23 |  |  |  |  |  |  | 
17. Publication of results (Embargo Period) 13-20 June |  |  |  |  |  | 13-20 |  |  |  |  |  | 
18. End of embargo - release of the WCY 2023 results |  |  |  |  |  | 20 |  |  |  |  |  | 
19. Press Release Meeting |  |  |  |  |  | 20 |  |  |  |  |  | 
20. Printed copies of the WCY to Partner Institutes |  |  |  |  |  |  | 30 |  |  |  |  | 
21. Talent Ranking (Tentative Release Date) |  |  |  |  |  |  |  |  | 21 |  |  | 
22. Subscription for IMD WCY REPORT 2024 |  |  |  |  |  |  |  |  |  | 17 |  | 
23. Digital Ranking (Tentative Release Date) |  |  |  |  |  |  |  |  |  |  | 30 | 
MPC’s Task