PAPER FOR APPROVAL

MPC BOARD OF MANAGEMENT (BOM)

| TITLE | Machinery & Equipment Productivity Nexus Virtual Advisory Clinic (MEVAC) - GEMBA |
| --- | --- |
| DATE / DURATION | February – May 2022 |
| OBJECTIVES AND BACKGROUND | In helping the business to revitalize their operations during unprecedented years, MEPN has introduced the Machinery & Equipment Productivity Nexus Virtual Advisory Clinic (MEVAC) to help businesses especially in M&E industry in rebuilding the business due to the adverse impact of COVID-19. In the past 2 years, the program have shown a significant approach to gather current industry issues and challenges. It also gauged some recommendation and solution for the business to mitigate the short term impact of Covid 19 and long term business competitiveness. As for 2022, MEPN would like to take reverse action whereby all appointed advisors will approach directly to some potential companies by conducting physical fact finding and interview session to have a better experience and understand on the company environment, process and problems. Hence, MEPN take initiative to organise the MEVAC with the objectives: - To serves as channel for Malaysian enterprises to raise matters of mutual interests, especially in the M&E sector - To diagnose company “sickness” and recommend implementable solutions in addressing the challenges and barriers for company’s growth and expansion; and - To support M&E industry capacity and capability to revitalise the business in the short and medium terms. |
| METHODS OF IMPLEMENTATION | Activities will be conducted both physically and virtually through fact finding activity and virtual advisory. |
| STAKEHOLDERS | - NGC Private Sectors: Machinery & Engineering Industries Federation (MEIF) and associations under its umbrella. - NGC Public Sectors: EPU, MITI, MIDA, MATRADE, SIRIM, HRD Corp and ILMIA. |
| EXPECTED OUTCOME | 1) Businesses received advisory and access to productivity tools for productivity improvement. 2) Businesses have a better understanding on how to address their company issues and challenges through internal intervention programmes. 3) MEPN able to collect relevant issue and challenges to strategise relevant facilitation, coordination, and intervention programmes for the participating companies. |
| EXPECTED OUPUT | - Program Process Flow - 200 real-time consultation - 50 GEMBA reports - 150 VAC reports - Evaluation Report - Facilitator Report |
| TARGET GROUP | - Machinery & Equipment (M&E) industry - Engineering Supporting Services (ESS) / Manufacturing Related Services (MRS) industry |
| BUDGET / ESTIMATED COST | MPB-MEPN; :; RM36,700.00. Operating Expenses (OE); :; RM3,000.00. Total; :; RM39,700.00. Note: Details, please refer to Appendix 1 |
| INCOME (RM) – IF ANY | - |
| RECOMMENDATION | The approval of BOM is sought to approve the budget of RM39,700.00 to utilize the MPB-MEPN budget for organising MEPN program: Machinery & Equipment Productivity Nexus Virtual Advisory Clinic (MEVAC), February – May 2022. |
| UNIT / DIVISION | Machinery and Equipment Productivity Nexus (MEPN), Delivery Management Office (DMO) |

**Please attach other relevant information if necessary.

(Examples: Program agenda, cost details, risk plan, diagrams, plan sketches, name lists, Gantt charts, etc.)

Only for applications that use Development Budget from other Units/Divisions. This column can be ignored if it is not relevant.

SUPPORTED BY: NAME OF OFFICER IN CHARGE OF THE DEVELOPMENT BUDGET Position: Budget Name: Date:

| PREPARED BY: Abdul Rahman Kamis Assistant Manager Date: 31/1/2022 | CHECKED BY: Azhani Ismail Manager Date: 31/1/2022 | APPROVED BY: Dr. Mohamad Norjayadi Tamam Director Date: 31/1/2022 |
| --- | --- | --- |

APPENDIX 1

BUDGET / ESTIMATED COST

Machinery & Equipment Productivity Nexus Virtual Advisory Clinic (MEVAC)

Followings are the partial costs involved for organising MEPN program: Machinery & Equipment Productivity Nexus Virtual Advisory Clinic (MEVAC), February – May 2022.

| No. | Item | Cost / Unit | Pax | Quantity | Total (RM) |
| --- | --- | --- | --- | --- | --- |
| - DEVELOPMENT BUDGET |  |  |  |  |  |
| - Administration |  |  |  |  |  |
| i. | VAC Moderator | RM250 | 1 | 40 hours | 10,000.00 |
| ii. | Press Release | RM1000 | 1 | 1 | 1,000.00 |
| - Virtual Advisory Clinic (VAC) |  |  |  |  |  |
| i. | Facilitator – Advisor | RM250 | 5 | 10 companies | 12,500.00 |
| - Fact Finding (GEMBA) |  |  |  |  |  |
| i. | Field Expert | RM400 | 5 | 2 companies | 4,000.00 |
| ii. | Report Writer (2 pages/ company) | RM200 | 5 | 4 pages | 4,000.00 |
| iii. | Expert Mileage Claim | RM100 | 5 | 2 trips | 1,000.00 |
| - Workshop to Develop GEMBA Template |  |  |  |  |  |
| i. | Half-Day Workshop Package | RM160 | 15 | 1 | 2,400.00 |
| ii. | Workshop Facilitator | RM250.00 | 1 | 4 hours | 1,000.00 |
| iii. | Experts | RM400.00 | 2 | 1 | 800.00 |
| Total A |  |  |  |  | 36,700.00 |
| - OPERATIONAL BUDGET |  |  |  |  |  |
| i. | Mileage Claim / Grab/ Teksi / Food Allowance | - | - | - | 2,000.00 |
| ii. | Accommodation | RM250 | 2 | 2 | 1,000.00 |
| Total B |  |  |  |  | 3,000.00 |
| Grand Total (A + B) |  |  |  |  | 39,700.00 |

Followings are the total costs involved for organising MEPN program: Machinery & Equipment Productivity Nexus Virtual Advisory Clinic (MEVAC), February – December 2022.

| No. | Item | Cost / Unit | Pax | Quantity | Total (RM) |
| --- | --- | --- | --- | --- | --- |
| - DEVELOPMENT BUDGET |  |  |  |  |  |
| - Administration |  |  |  |  |  |
| i. | VAC Moderator | RM250 | 1 | 40 hours | 10,000.00 |
| ii. | Press Release | RM1000 | 1 | 2 | 2,000.00 |
| iii. | Program Report Writer | RM200 | 1 | 10 pages | 2,000.00 |
| - Virtual Advisory Clinic (VAC) |  |  |  |  |  |
| i. | Facilitator – Advisor | RM250 | 5 | 30 companies | 37,500.00 |
| - Fact Finding (GEMBA) |  |  |  |  |  |
| i. | Field Expert | RM400 | 5 | 10 companies | 20,000.00 |
| ii. | Report Writer (2 pages/ company) | RM200 | 5 | 20 pages | 20,000.00 |
| iii. | Expert Mileage Claim | RM100 | 5 | 10 trips | 5,000.00 |
| - Workshop to Develop GEMBA Template |  |  |  |  |  |
| i. | Half-Day Workshop Package | RM160 | 15 | 2 | 4,800.00 |
| ii. | Workshop Facilitator | RM250.00 | 1 | 8 hours | 2,000.00 |
| iii. | Experts | RM400.00 | 2 | 2 | 1,600.00 |
| Total A |  |  |  |  | 104,900.00 |
| - OPERATIONAL BUDGET |  |  |  |  |  |
| i. | Mileage Claim / Grab/ Teksi / Food Allowance | - | - | - | 6,000.00 |
| ii. | Accommodation | RM250 | 5 | 5 | 6,250.00 |
| Total B |  |  |  |  | 12,250.00 |
| Grand Total (A + B) |  |  |  |  | 117,150.00 |