KERTAS CADANGAN UNTUK PERTIMBANGAN

LEMBAGA PENGURUSAN MPC (BOM MAKLUMAN)

| TAJUK Keterangan: Tajuk Projek/ Cadangan | Technical Working Group Food Cost Activities and Initiatives for Year 2023 |
| --- | --- |
| TARIKH/ GARIS MASA Keterangan: Jadual mula dan akhir pelaksanaan projek/ cadangan | June 2023 – October 2023 |
| TUJUAN & LATAR BELAKANG Keterangan: Tujuan dan penerangan ringkas mengenai projek | This BOM PAPER is to inform the BOD Members on the extension of date from June 2023 till October 2023. TWGFC has thus far used RM5,700 for the services of rapporteur (RM3000), food package (RM1500) and SME services (RM1200). All TWGFC meetings are held in MPC premises, therefore only expenses on food package and rapporteur services were required. Also included the revised costing for the TWGFC as seen in Estimated Cost and the Gantt chart for TWGFC activities planned for the year 2023. The objectives of the Technical Working Group Food Cost are: - Promotes ease of doing business through Public-Private Partnership. - Improve business regulations to enhance productivity and competitiveness. - Proactively launch and pursuance of new improvement initiatives. |
| JUSTIFIKASI Keterangan: Penjelasan yang menyokong kepada pelaksanaan projek/ cadangan | The establishment of PEMUDAH has resulted in positive achievements in accelerating public-private sector initiatives in facilitating the way of doing business. The achievements were also recognized by various international bodies including the World Bank, the World Economic Forum and the Institute for Management Development (IMD). To continue the momentum of this achievement, the Cabinet Meeting on 26 November 2021 has agreed that the role of PEMUDAH be strengthened and its membership improved to balance the need to boost the delivery system regulation and at the same time improve the efficiency of the industry. |
| KAEDAH PELAKSANAAN Keterangan: Kaedah yang perlu dilakukan bagi melaksanakan projek | - To study the World Competitiveness Yearbook (WCY) Framework on Economic Performance for criteria (Food Cost) and provide specific recommendation. - To analyse concerns raised by relevant stakeholders or affected parties regarding the sub-factor of Economic Performance (Food Cost) and to propose specific improvement to be implemented by the process owner. - To monitor and report to PEMUDAH on the issues and outcomes encountered to enhance competitiveness of the country. |
| STAKEHOLDERS/ PIHAK BERKEPENTINGAN Keterangan: Pihak atau kumpulan yang menerima kesan positif mahupun negatif daripada projek yang dijalankan | - Ministries - Agencies - Pihak Berkuasa Tempatan (PBT) - Business Association - Business Community |
| JANGKAAN HASIL/ OUTCOME Keterangan: Apa yang MPC perlu capai/ faedah-faedah jangka pendek dan jangka panjang hasil dari intervensi projek/ cadangan | - Comprehensive report on the initiatives and activities of Technical Working Group Food Cost. - Well-informed regulators on matters relating to Food Cost on designing public policy. |
| JANGKAAN OUTPUT Keterangan:Output ketara dan tidak ketara yang dihasilkan daripada aktiviti projek/ cadangan. | - Report on the initiatives and activities of Technical Working Group Food Cost |
| KUMPULAN SASAR Keterangan: Individu/ kumpulan yang menerima faedah daripada projek/ cadangan | - Ministries - Agencies - Pihak Berkuasa Tempatan (PBT) - Business Association |
| SUMBER BAJET/ KOS Keterangan: Sumber bajet / jumlah kos yang terlibat. | RM32,200 (DE (Budget FORE 2023) |
| HASIL (RM) - SEKIRANYA ADA Keterangan: Pendapatan yang diterima daripada projek | N/A |
| SYOR Keterangan: Keputusan yang diperlukan daripada Lembaga Pengurusan MPC | Apply for BOM approval for the Technical Working Group Food Cost Activities and Initiatives |
| UNIT/ BAHAGIAN | Seksyen Daya Saing Negara/ PCD |

**Sila lampirkan maklumat-maklumat lain yang berkaitan sekiranya perlu.

(Contoh: Agenda program, perincian kos, pelan risiko, gambar rajah, lakaran pelan, senarai nama, carta Gantt, dll.)

Estimated Cost

| NO. | PHASE | ITEM | ESTIMATED COST (RM) | TOTAL (RM) |
| --- | --- | --- | --- | --- |
| 1. | ADVOCACY | MEDIA STATEMENT RM1,000 X 2 MEDIA STATEMENT | 2,000.00 | 11,000.00 |
|  |  | TWGFC INITIATIVES AND ACTIVITIES - FEE FOR RAPPORTEUR RM100 X 10 PAGES = RM1000 - FACILITATOR RM2000 X 4 DAYS = RM8000 | 9,000.00 |  |
| 2. | ADVISORY | HIRING OF SMES TO SHARE KNOWLEDGE AND EXPERIENCE AND CONDUCT OF INTERVIEWS WITH SELECTED MINISTRIES/AGENCIES PBT’S OR BUSINESS ASSOCIATION. RM400 X 3 HOURS = RM1,200 | 1,200.00 | 1,200.00 |
| 3 | COORDINATION | ENGAGEMENTS WITH TWGFC STAKEHOLDERS (MEETING PACKAGES) (RM5000 X 2 SESSIONS) | 10,000 | 15,000.00 |
|  |  | ENGAGEMENTS WITH TWGFC STAKEHOLDERS (FOOD & BEVERAGES MEETING ATTENDEES) (RM500X 10 SESSIONS) | 5,000 |  |
| TOTAL |  |  |  | 27,200.00 |

Hanya untuk permohonan yang menggunakan Bajet Pembangunan dari Unit/Bahagian lain. Kolum ini boleh diabaikan sekiranya tidak berkaitan.

DISOKONG OLEH: NAMA PEGAWAI PENJAGA BAJET PEMBANGUNAN Jawatan: Nama Bajet: Tarikh:

| **Wajib diisi | **Wajib diisi | Permohonan memadai disemak sehingga peringkat Penyelia. Kolum ini boleh diabaikan sekiranya tidak berkaitan |
| --- | --- | --- |
| DISEDIAKAN OLEH: SHANTHINI TAMADORAM Penolong Pengurus 9 June 2023 | DISEMAK OLEH: NORHASIMAH IBRAHIM Timbalan Pengarah 9 June 2023 | DISAHKAN OLEH: WAN FAZLIN NADIA WAN OSMAN Pengarah 9 June 2023 |

APPENDIX 1

GANTT CHART FOR TWGFC ACTIVITIES FOR YEAR 2023