## Slide 1
TIMELINE FOR DEVELOPMENT OF GUIDELINE ON PERFORMANCE-BASED CONTRACT FOR CLEANING INDUSTRY
No | Activity | Date
1 | Develop guidelines and mechanisms for implementing performance-based contracts in the cleaning industry. | Completed Week 1 & 2 June
2 | Gather insights from ministries and cleaning industry stakeholders regarding the adopted and adapted guidelines and mechanisms. | Completed 20 June 2023
3 | Refine the guidelines and mechanisms based on stakeholder feedback. | Completed Week 3 & 4 June
4 | Present the performance-based contract proposal to the Minister of Economy | Week 1 Aug
5 | Refine the Implementation Mechanism based on Feedback from YB | Week 2 Aug

## Slide 2
No | Activity | Date
1 | Develop draft mechanisms to implement a PWM | Completed Week 1 & 2 June
2 | Gather feedback from industry stakeholders on the implementation of PWM | Completed 20 June 2023
3 | Refine the mechanisms to implement the PWM | In Progress Week 3 July
4 | Establish wage tiers and criteria for progression, including skill and competency frameworks | Week 4 July
5 | Strengthen training and upskilling programmes | Week 4 July
6 | Presentation to the Minister of Economy | Week 1 Aug
7 | Refine the implementation mechanism based on feedback from YB | Week 2 Aug
TIMELINE FOR DEVELOPMENT OF UPSKILLING PROGRAMMES AND PROGRESSIVE WAGE MODEL (PWM) FOR CLEANING INDUSTRY WORKERS

## Slide 3
TIMELINE FOR DEVELOPMENT OF FINANCIAL FRAMEWORK FOR TECHNOLOGY ADOPTION FOR CLEANING INDUSTRY
No | Activity | Date
1 | Conduct an analysis of the cleaning industry, including current trends, challenges, and opportunities | Completed Week 1 & 2 June
2 | Gather insights from key stakeholders to understand their needs, concerns, and expectations regarding technology adoption and financial support | Completed 20 June 2023
3 | Design a financial framework that addresses the specific requirements of the cleaning industry | Completed Week 3 & 4 June
4 | Refine the financial framework | Week 3 July
5 | Present the proposal to the Minister of Economy | Week 1 Aug
6 | Refine the Implementation Mechanism based on Feedback from YB | Week 2 Aug

## Slide 4
TIMELINE FOR PILOT PROJECT AT SELECTED PREMISES
No | Activity | Date
1 | Identify a suitable location or group for conducting a pilot project | Aug – Dec 2023
2 | Implement the framework/ model on a smaller scale in the selected setting | Aug – Dec 2023
3 | Monitor and evaluate the impact of the model on wages and worker outcomes | 
4 | Collect data and feedback to assess the effectiveness of the model in a real-world scenario | 
5 | Refine the mechanism based on the Pilot Project | Dec 2023
6 | Rollout Nationwide Implementation. | 2024

## Slide 5
TIMELINE TO CONDUCT REGULATORY IMPACT ANALYSIS (RIA) (1/2)
No | Activity | Date
1 | Pre-Commencement Kick-off Meeting including scoping & planning | August W1
2 | Data and Information Gathering on existing framework | August W2
3 | Submission of Digital Regulatory Notification (DRN) | August W2
Initial RIS Assessment | Initial RIS Assessment | 
5 | Element 1: Problem Statement Identification of issues, data and other supporting evidence | August W3-4
6 | Element 2: Objectives Identifying objectives for the intervention | August W3-4
7 | Element 3: Options Identifying options including status quo, regulatory, and non-regulatory | August W3-4
8 | Element 4: Impact Analysis Identifying costs and benefits associated to the intervention | August W4 – September W4

## Slide 6
TIMELINE TO CONDUCT REGULATORY IMPACT ANALYSIS (RIA) (2/2)
No | Activity | Date
Final RIS Assessment | Initial RIS Assessment | 
9 | Element 5: Consultation (Minimum 30 days, UPC/other platforms) Preparation of consultation documents (proposal, questionnaires, slide deck etc.) Conducting consultation with key stakeholders | October - November
10 | Element 6: Conclusion and Recommendation | November
11 | Element 7: Strategy for Implementation Preparation of communication, enforcement and monitoring & evaluation plan | Novermber
12 | RIS Adequacy Assessment | December
13 | Presentation of RIS findings [PEMUDAH] | December