KERTAS CADANGAN UNTUK PERTIMBANGAN

LEMBAGA PENGURUSAN MPC

| TAJUK Keterangan: Tajuk Projek/ Cadangan | The Publication of National Behavioural Insights (BI) Guideline |
| --- | --- |
| TARIKH/ GARIS MASA Keterangan: Jadual mula dan akhir pelaksanaan projek/ cadangan | July 2023 - December 2023 |
| TUJUAN & LATAR BELAKANG Keterangan: Tujuan dan penerangan ringkas mengenai projek | The objectives of the National BI Guideline are: - To serve as a guide in applying behavioural insights to public policy from the beginning to the end of the policy cycle; - To serve as a repository of best practices, proof of concepts and methodological standards for behavioural insights practitioners and policymakers; and - To provide general principles for the ethical application of BI and guidelines where ethical concerns might be raised for specific issues. |
| JUSTIFIKASI Keterangan: Penjelasan yang menyokong kepada pelaksanaan projek/ cadangan | MPC has been mandated by the government to undertake BI programs and initiatives for Malaysia year 2020 onwards. Publishing a BI Guideline that best suits the nation’s culture that includes individual, environment, and social factors especially in every stage of the policy cycle is essential in order to provide better quality and more effective regulations. The National BI Guideline published in Bahasa Malaysia will serve greater purpose to its readers and practitioners. |
| KAEDAH PELAKSANAAN Keterangan: Kaedah yang perlu dilakukan bagi melaksanakan projek | - To assess Malaysia’s current design and implementation of public policy; - To conduct research of existing behavioural theories, methodologies, public policy issues and challenges; and - To establish a BI Guideline that includes designing solutions to ensure that policies reflect real needs and behaviours for greater impact and effectiveness. |
| STAKEHOLDERS/ PIHAK BERKEPENTINGAN Keterangan: Pihak atau kumpulan yang menerima kesan positif mahupun negatif daripada projek yang dijalankan | - Ministries - Agencies - Pihak Berkuasa Tempatan (PBT) |
| JANGKAAN HASIL/ OUTCOME Keterangan: Apa yang MPC perlu capai/ faedah-faedah jangka pendek dan jangka panjang hasil dari intervensi projek/ cadangan | - Integrated BI Guideline to be used at national level. - Application of the National BI Guideline in case studies. - Well-informed regulators on matters relating to BI on designing public policy |
| JANGKAAN OUTPUT Keterangan:Output ketara dan tidak ketara yang dihasilkan daripada aktiviti projek/ cadangan. | - 1 National BI Guideline for Ministries (Transalation to Bahasa Malaysia) - 15 Advisory meetings - 8 Engagement sessions with ministeries |
| KUMPULAN SASAR Keterangan: Individu/ kumpulan yang menerima faedah daripada projek/ cadangan | - Ministries - Agencies - Pihak Berkuasa Tempatan (PBT) |
| SUMBER BAJET/ KOS Keterangan: Sumber bajet / jumlah kos yang terlibat. | RM76,000.00 (Bajet RMK-12 BEHAVIOURAL INSIGHTS (BI)) (As in Appendix) |
| HASIL (RM) - SEKIRANYA ADA Keterangan: Pendapatan yang diterima daripada projek | N/A |
| SYOR Keterangan: Keputusan yang diperlukan daripada Lembaga Pengurusan MPC | Apply for BOM approval for the development of the Behavioral Insights Guidelines for year 2023 |
| UNIT/ BAHAGIAN | Seksyen Daya Saing Negara/ PCD |

**Sila lampirkan maklumat-maklumat lain yang berkaitan sekiranya perlu.

(Contoh: Agenda program, perincian kos, pelan risiko, gambar rajah, lakaran pelan, senarai nama, carta Gantt, dll.)

Project Phase

| PHASE | ACTIVITY |
| --- | --- |
| Development | Development of BI Guideline tailored specifically for the ministries and monitoring of intervention projects in (Translation to Bahasa Malaysia) |
| Advisory | - Projects identified in Ministries. - Training to ministries as a preparation before embarking on the projects. |
| Coordination | Embark on projects with selected stakeholders. |

Estimated Cost

| NO | PHASE | ITEM | ESTIMATED COST (RM) | TOTAL (RM) |
| --- | --- | --- | --- | --- |
| 1. | Development | Digital Publication BI Guideline (Translation works) | 20,000.00 | 20,000.00 |
| 2. | Advisory | Hiring of to Share Knowledge and Experience Through Training and Reporting on National Bi Guideline Case Studies 3 Sessions x RM400 x 2 hours = RM2400 RM2400 X 5 Case Studies x 2 SMEs | 24,000.00 | 24,000.00 |
| 3. | Coordination | BI Engagements session with Ministries (RM200 X 20 pax X 4 days) x 2 times a year | 32,000.00 | 32,000.00 |
| TOTAL (RM) |  |  |  | 76,000.00 |

Hanya untuk permohonan yang menggunakan Bajet Pembangunan dari Unit/Bahagian lain. Kolum ini boleh diabaikan sekiranya tidak berkaitan.

DISOKONG OLEH: NAMA PEGAWAI PENJAGA BAJET PEMBANGUNAN Jawatan: Nama Bajet: Tarikh:

| **Wajib diisi | **Wajib diisi | Permohonan memadai disemak sehingga peringkat Penyelia. Kolum ini boleh diabaikan sekiranya tidak berkaitan |
| --- | --- | --- |
| DISEDIAKAN OLEH: SHANTHINI TAMADORAM Penolong Pengurus 21 July 2023 | DISEMAK OLEH: NORHASIMAH IBRAHIM Timbalan Pengarah 21 July 2023 | DISAHKAN OLEH: MOHAMMED ALAMIN REHAN Pengarah 21 July 2023 |