KERTAS CADANGAN UNTUK PERTIMBANGAN

LEMBAGA PENGURUSAN MPC

| TAJUK Keterangan: Tajuk Projek/ Cadangan | ESTABLISHMENT OF MYMUDAH UNIT THROUGH TECHNICAL WORKING ON GROUP SUSTAINABLE DEVELOPMENT GOALS (TGWSDG) |
| --- | --- |
| TARIKH/ GARIS MASA Keterangan: Jadual mula dan akhir pelaksanaan projek/ cadangan | August 2023 – November 2023 |
| TUJUAN & LATAR BELAKANG Keterangan: Tujuan dan penerangan ringkas mengenai projek | TWGSDG aims to gather insights and assess the status of the Care Economy in Malaysia. It also aims to facilitate information sharing and discussions about the broader direction of the Care Economy. These engagements will involve policymakers, industry representatives, academics, researchers, civil society organizations (CSOs), media, and other stakeholders. Aligned with these initiatives, TWGSDG will guide stakeholders to establish a "MyMudah" unit within their respective Ministries and associations. The purpose of this unit is to address issues and propose recommendations for optimal solutions. The establishment of the MyMudah unit also serves to promote solutions for reducing unnecessary regulatory burdens. Furthermore, these activities will lead to enhancements in several indicators of national competitiveness, including Female Labor Force participation, Workforce dynamics, and Digitalization. The ultimate goal is to contribute to the country's economic recovery, foster sustainable economic growth, and stimulate significant productivity gains. |
| JUSTIFIKASI Keterangan: Penjelasan yang menyokong kepada pelaksanaan projek/ cadangan | TWGSDG is dedicated to comprehending Malaysia's Care Economy and facilitating inclusive dialogues among policymakers, industry representatives, and academics to chart its trajectory. Through the establishment of "MyMudah" units and targeted enhancements in workforce, female labor force participation, and digitalization, TWGSDG is committed to streamlining processes, fostering economic growth, and nurturing a prosperous future for Malaysia. The nation's productivity and competitiveness. The achievements will also be recognized by various international bodies including the World Bank, the World Economic Forum, and the Institute for Management Development (IMD). |
| KAEDAH PELAKSANAAN Keterangan: Kaedah yang perlu dilakukan bagi melaksanakan projek | - To establish a MyMudah unit at Ministries & Business Associations - To study the World Competitiveness Ranking (WCR) Framework on indicator Female Labor Force, Digital, Workforce and provide specific recommendation especially which related to the care economy. - To analyse concerns raised by relevant stakeholders or affected parties regarding the indicators and to propose specific improvement to be implemented by the process owner thru a strategic engagement. - To monitor and report to PEMUDAH on the issues and outcomes encountered to enhance competitiveness of the country. |
| STAKEHOLDERS/ PIHAK BERKEPENTINGAN Keterangan: Pihak atau kumpulan yang menerima kesan positif mahupun negatif daripada projek yang dijalankan | - Ministries - Agencies - Local State Authority (PBT) - Business Association - Business Community |
| JANGKAAN HASIL/ OUTCOME Keterangan: Apa yang MPC perlu capai/ faedah-faedah jangka pendek dan jangka panjang hasil dari intervensi projek/ cadangan | - Well-informed regulators on matters relating to Sustainable Development Goals on designing public policy with related to specific indicators through the establishment of MyMudah unit - A sustainable and robust Care Economy to enhance the nation's productivity and competitiveness based on WCR indicators |
| JANGKAAN OUTPUT Keterangan:Output ketara dan tidak ketara yang dihasilkan daripada aktiviti projek/ cadangan. | - Establishment of MyMudah units - Report on the initiatives and activities of TWGSDG based on the improved indicators. |
| KUMPULAN SASAR Keterangan: Individu/ kumpulan yang menerima faedah daripada projek/ cadangan | - Ministries - Agencies - Local State Authority (PBT) - Business Association - Business Community |
| SUMBER BAJET/ KOS Keterangan: Sumber bajet / jumlah kos yang terlibat. | RM20,000 (MyMudah) RM10,000 (RM40) RM 5,000 (PCD Operation Budget) |
| HASIL (RM) - SEKIRANYA ADA Keterangan: Pendapatan yang diterima daripada projek | N/A |
| SYOR Keterangan: Keputusan yang diperlukan daripada Lembaga Pengurusan MPC | The approval of the Board of Management (BOM) is sought for Establishment of MyMudah unit through Technical Working On Group Sustainable Development Goals (TGWSDG) |
| UNIT/ BAHAGIAN | National Competitiveness Section/ PCD |

**Sila lampirkan maklumat-maklumat lain yang berkaitan sekiranya perlu.  (Contoh: Agenda program, perincian kos, pelan risiko, gambar rajah, lakaran pelan, senarai nama, carta Gantt, dll.

Estimated Cost

| No. | Phase | Item | Estimated Cost (Rm) | Total (Rm) |
| --- | --- | --- | --- | --- |
| 1. | Coordination (MyMudah) | - Engagements with Stakeholders (Events, Forums, Meeting Packages and Food & Beverages Meeting Attendees) | 20,000.00 | 20,000.00 |
| 2. | Advisory & Advocacy (RM40) | - Facilitator /SME/Speaker - Media Statement | 10,000.00 | 10,000.00 |
| 3. | Promotion & Fee (Operational) | - Video, Promotional Items, Participation Fee | 5,000.00 | 5,000.00 |
| Total |  |  |  | 35,000.00 |

Hanya untuk permohonan yang menggunakan Bajet Pembangunan dari Unit/Bahagian lain. Kolum ini boleh diabaikan sekiranya tidak berkaitan.

DISOKONG OLEH: NAMA PEGAWAI PENJAGA BAJET PEMBANGUNAN Jawatan: Nama Bajet: Tarikh:

| **Wajib diisi | **Wajib diisi | Permohonan memadai disemak sehingga peringkat Penyelia. Kolum ini boleh diabaikan sekiranya tidak berkaitan |
| --- | --- | --- |
| DISEDIAKAN OLEH: SITI NUR SYUHAIDA Penolong Pengurus 28 Ogos 2023 | DISEMAK OLEH: NORHASIMAH IBRAHIM Timbalan Pengarah 28 Ogos 2023 | DISAHKAN OLEH: ALAMIN REHAN Pengarah 28 Ogos 2023 |