TIMELINE

DEVELOPING INDUSTRY PROFILE FOR AUTOMOTIVE INDUSTRY

| Activities | 2024 |  |  |  |
| --- | --- | --- | --- | --- |
|  | Jan | Feb | Mar | Apr |
| Procurement |  |  |  |  |
| Project Initiation and Planning - Discuss on the overview of the industry profile. - Gather data on market trends, key players, and relevant statistics. |  |  |  |  |
| Stakeholder Engagement - Schedule and conduct sessions with industry experts for in-depth discussions. - Gather feedback on preliminary findings and insights. - Document key findings and areas of focus for the industry profile. |  |  |  |  |
| 1st Draft Report - Revise the report based on received feedback to address any concerns or suggestions. |  |  |  |  |
| Final Draft and Proofreading - Revise final draft of the industry profile. - Conduct a thorough proofreading for grammar, spelling, and formatting. |  |  |  |  |