ATTACHMENT 1

ESTIMATED TOTAL COST NDFB

| KOD | ITEM | COST (RM) | TOTAL COST (RM) DEVELOPMENT BUDGET |
| --- | --- | --- | --- |
| A: Budget : FORE |  |  |  |
| P29105 | Fasilitator (Outreach) | - RM 1,800 (Physical) x 6 sessions x 1 fasilitators | 169,200.00 |
|  | Fasilitator (Chapter 2) | - RM 1,800 (Physical) x 4 sessions x 2 days x 11 fasilitators |  |
| P29105 | Subject Matter Expert (SMEs) | RM400 x 10 sesions x 4 hours x 11 SMEs | 176,000.00 |
| P29112 | Report Writing (Outreach) | RM200 x 15 pages x 11 reports | 33,000.00 |
|  | Report Writing (Chapter 2) | RM200 x 10 pages x 11 reports | 22,000.00 |
|  | Presentation Slide | RM100 x 20 page slides x 11 chapter | 22,000.00 |
| P29407 | Full Day Meeting/Seminar Package | RM160 x 40 paxs x 5 session RM180 x 200 paxs x 1 session (Central) | 32,000.00 36,000.00 |
| P29112 | Media Statement | RM1,000 x 10 set | 10,000.00 |
| TOTAL COST |  |  | 500,200.00 |

| NO | ITEM | COST (RM) | TOTAL COST (RM) DEVELOPMENT BUDGET |
| --- | --- | --- | --- |
| B: Budget : OPERATIONAL |  |  |  |
| 1 | Claims Pegawai MPC (Mileage, Meals, Taxi/Grab etc.) | RM500 X 5 pax X 6 Programmes | 15,000.00 |
| 2 | Return Flight Ticket: Domestic | RM500 X 5 pax X 6 Programmes | 15,000.00 |
| 3 | Accommodation | RM220 X 2 Night X 5 Pax X 6 Programmes | 13,200.00 |
| TOTAL COST |  |  | 43,200.00 |

ATTACHMENT 2

TIMELINE

| NO. | ACTIVITY | START DATE | END DATE |
| --- | --- | --- | --- |
| 1. | Identify Subject Matter Experts (SMEs) and obtain the resumes | 22/12/2023 | 29/12/2023 |
| 2. | Submit SME’s names and resume to Ministry of Economy | 30/12/2023 | - |
| 3. | Appointment of SMEs | 2/1/2024 | - |
| 4. | Onboarding Session with MPC Associates | 2/1/2024 | - |
| 5. | Develop Action Plans | 3/1/2024 | 7/1/2024 |
| 6. | Brainstorming Session | 5/1/2024 | - |
| 7. | Project Kick off and Analysis of stakeholders | 8/1/2024 | 10/1/2024 |
| 8. | Identify issues and challenges on regulatory burdens from businesses | 11/1/2024 | 21/1/2024 |
| 9. | Consultation/ validation sessions with businesses, regulators and other stakeholders | 22/1/2024 | 4/2/2024 |
| 10. | Obtain feedback from regulators | 5/2/2024 | 18/2/2024 |
| 11. | Develop recommendations to improve quality of regulations | 19/2/2024 | 3/3/2024 |
| 12 | Submit the report on annual review comprises of options, recommendations and feedback from regulators to reduce regulatory burden on businesses | 4/3/2024 | - |

ATTACHMENT 3

PHYSICAL ENGAGEMENTS: SCHEDULE

| NO | LOCATION | DATE |
| --- | --- | --- |
| 1. | East Coast (Kuantan) | 1 February 2024 (Thursday) |
| 2. | Southern (Johor Bahru) | 1 February 2024 (Thursday) |
| 3. | Central (Putrajaya) | 6 February 2024 (Tuesday) |
| 4. | Northern (Seberang Prai) | 13 February 2024 (Tuesday) |
| 5. | Sabah (Kota Kinabalu) | 14 February 2024 (Wednesday) |
| 6. | Sarawak (Kuching) | 15 February 2024 (Thursday) |