KERTAS CADANGAN UNTUK PERTIMBANGAN

LEMBAGA PENGURUSAN MPC (BOM)

| TAJUK Keterangan: Tajuk Projek/ Cadangan | Compilation of Productivity Frontier Companies; Vendor Development to Malaysian companies in the E&E Industry Continuing from 2021’s project |
| --- | --- |
| TARIKH/ GARIS MASA Keterangan: jadual mula dan akhir pelaksanaan projek/ cadangan | January – April 2022 (Please Refer Appendix 1) |
| TUJUAN & LATAR BELAKANG Keterangan: tujuan dan penerangan ringkas mengenai projek | The Electrical and Electronics Productivity Nexus (EEPN) was established under the Malaysia Productivity Blueprint (MPB) with the theme on “Driving Productivity of the Nation”. EEPN Strategic Initiative 1 (SI#1) is conducting the compilation of Productivity Practices of Frontier Companies; Vendor Development of the E&E Industry in Malaysia. 2. The objective of this study is to identify best practices in developing local ecosystems (to transfer of knowledge and technologies to Malaysian companies) by large Malaysian companies and MNCs. Local SMEs and National Champions (“National Frontiers”) can emulate MNCs (“Global Frontiers”) and improve their performance and productivity by combining better inputs [“The Future of Productivity”, OECD (2015)]:- i. New ideas; ii. Technological innovations; iii. New business models; and iv. More efficient resource allocation. 3. This project has started in Q4 of 2021, whereby 3 companies has answered the survey questionnaire and 1 company has participated the interview session dated 19th November 2021 with Greatech Integration (M) Sdn. Bhd. In 2022, the team plans to interview 5 companies in getting their inputs. |
| KAEDAH PELAKSANAAN Keterangan: kaedah yang perlu dilakukan bagi melaksanakan projek | This project will be implemented through appointed facilitators, from JPPK database. All activities will be conducted virtually. The study will be on approximately 10 companies, some of the potential companies to be included in the study are: i. Intel ii. Keysight iii. Firstsolar iv. Jabil v. Plexus vi. Flex vii. Infineon; viii. TI ix. ST Micro x. Greatech ( completed) xi. Vitrox xii. Honeywell. |
| STAKEHOLDERS/ PIHAK BERKEPENTINGAN Keterangan: pihak atau kumpulan yang menerima kesan positif mahupun negatif daripada projek yang dijalankan | - Captains of E&E industry, MNCs, LLCs and SMEs - EEPN Governing Committee - Related ministries and agencies |
| JANGKAAN HASIL/ OUTCOME Keterangan: apa yang MPC perlu capai/ faedah-faedah jangka pendek dan jangka panjang hasil dari intervensi projek/ cadangan | - Diffusion of competencies from frontier companies to local SMEs, in terms of technology transfers, innovations and productivity best practices - Recommendations to institutionalize and emulate/spread the development of vendor/ supplier in Malaysia |
| JANGKAAN OUTPUT Keterangan: output ketara dan tidak ketara yang dihasilkan daripada aktiviti projek/ cadangan. | - Survey questionnaires reports - Best practices reports Of Productivity Frontier Companies; Vendor Development in the E&E Industry in Malaysia |
| KUMPULAN SASAR Keterangan: individu/ kumpulan yang menerima faedah daripada projek/ cadangan | E&E Companies |
| SUMBER BAJET/ KOS Keterangan: sumber bajet / jumlah kos yang terlibat. | MPB-EEPN : RM54,400.00 (Please Refer Appendix 1) |
| HASIL (RM) - SEKIRANYA ADA Keterangan: pendapatan yang diterima daripada projek | - |
| SYOR Keterangan: permohonan yang diperlukan daripada Lembaga Pengurusan MPC |  |
| UNIT/ BAHAGIAN | Electrical & Electronics Productivity Nexus (EEPN) |

**Sila lampirkan maklumat-maklumat lain yang berkaitan sekiranya perlu.

(Contoh: Agenda program, pelan risiko, gambar rajah, lakaran pelan, senarai nama, dll.)

DISOKONG OLEH: NAMA PEGAWAI PENJAGA BAJET Jawatan: Nama Bajet: Tarikh: **Hanya untuk permohonan yang menggunakan Bajet Pembangunan dari Unit/Bahagian lain. Kolum ini boleh diabaikan sekiranya tidak berkaitan.

| DISEDIAKAN OLEH: Nurul Nadia Zainal Adnan Project Manager Tarikh:19/1/2022 | DISEMAK OLEH: Lee Wan Wei Programme Manager Date: 19/1/2022 | DISAHKAN OLEH: Dr Mohamad Norjayadi Tamam Director Date: 19/1/2022 |
| --- | --- | --- |

APPENDIX 1

# 1.0 Project Timeline (Jan – April)

|  | Activity | Jan | Feb | Mar | Apr |
| --- | --- | --- | --- | --- | --- |
| 1 | Forming committee with industry captain |  |  |  |  |
| 2 | Data Gathering |  |  |  |  |
| 3 | Analysis of Findings and Interim Review |  |  |  |  |
| 4 | Engagement with Stakeholders (Final draft report) |  |  |  |  |
| 5 | Final report |  |  |  |  |

# 2.0 Estimated cost

The overall cost of the project is RM54,400.00 as shown in the table below:

| No. | Item | Cost | Quantity | Budget | Total (RM) |
| --- | --- | --- | --- | --- | --- |
| 1. | Writer - Best practices report - Press release - Newsletter | RM200/page | 100 pages | MPB-EEPN | 20,000.00 |
| 2. | Industrial expert | RM400/hour | 26 hours | MPB-EEPN | 10,400.00 |
| 3. | Proof reading | RM150/page | 100 pages | MPB-EEPN | 15,000.00 |
| 4. | Printing and publication - Design Charges, Layout and Printing - Idea, Conceptual & Art Direction - Colour and Photo Manipulation - Design of infographics - Final Artwork in PDF format for online publication, printing and raw file - Printing charges | RM9,000 | - | MPB-EEPN | 9,000.00 |
| Total Cost |  |  |  |  | 54,400.00 |