PROPOSAL PAPER FOR THE CONSIDERATION OF

MPC BOARD OF MANAGEMENT (BOM)

| TITLE Description: Project Title/ Proposal | Developing Business Supply Chain Frameworks for 14 Productivity Nexus |
| --- | --- |
| DATE/ TIMELINE Description: Start and end schedule of the project / proposal execution | August – October 2024 |
| PURPOSE & BACKGROUND Description: Purpose and brief background of the project | The business supply chain is a critical component of modern business operations, encompassing the entire process from company establishment to producing and delivering goods and services from raw materials to end consumers. It involves a network of regulators, suppliers, manufacturers, distributors, retailers, and logistics providers, each playing a vital role in ensuring the efficient flow of activities starting from business start-up, purchasing of raw materials, production, and product delivery. Each sector has a different supply chain due to the unique nature of its products, processes, and market demands. This project aims to develop a supply chain framework for 14 productivity nexuses, essential for optimizing operational efficiency, reducing costs, enhancing customer satisfaction, and managing risks. By analyzing the dynamic network within the supply chain of each sector, MPC can identify bottlenecks, leverage best practices, and implement innovative solutions to achieve exponential productivity growth in the future. Additionally, the findings from this project will also be utilized as input in developing proposals for RMKe-13. The objectives of this project are as follows: - To identify specific regulators, suppliers, manufacturers, distributors, retailers, and logistics providers involved in the supply chains of 14 sub-sectors; - To map the supply chain flows starting from company registration, raw materials, production to end consumers from local and global markets; and - To develop 14 supply chain frameworks for 14 productivity nexuses. |
| EXPECTED RESULTS/ OUTCOME Description: What MPC needs to achieve/ short-term and long-term benefits as a result of the project/ proposal intervention | Proposals for RMKe13 based on current state of existing frameworks that can: - Improve productivity and efficiency in business registration and establishment in Malaysia; - Enhance process efficiency in production floor; - Reduce operational costs in product delivery; - Establish standards for exporting; and - Strengthen global competitiveness through robust business ecosystem. |
| IMPLEMENTATION METHOD Description: Start and end schedule of the project/ proposal execution | - Drafting a supply chain framework for each sector; - Validating the framework with stakeholders; and - Establishing 14 frameworks for 14 Productivity Nexus. Implementation method to gather input and validation: - Workshops - Round Table Discussion |
| STAKEHOLDERS Description: Parties or groups that positively or negatively affected from the project | - Industry players - Industry associations - Local authority and SSM |
| EXPECTED OUTPUT Description: Tangible and intangible outputs generated from the project/ proposal activities | - Improve clarity on regulatory requirements for business registration and establishment in Malaysia; - Enhance the understanding of regulatory requirements on import (raw materials) and export (end products); and - Establish 14 comprehensive supply chain frameworks from raw materials to export. |
| TARGET GROUP Description: Individuals/ groups who benefit from the project/ proposal | 14 Productivity Nexus |
| SOURCE OF BUDGET/ COST Description: Source of budget / total costs involved | NO; ITEM; COST (RM). A.; OPERATIONAL BUDGET. 1.; Meeting Package: RM180 x 60 pax x 14 workshops - Engagement with industries; 151,200.00. 2.; Facilitator: RM1,800 x 1 day x 14 workshops; 25,200.00. 3.; Subject Matter Expert: RM400 x 4 hours x 14 pax x 2 sessions; 44,800.00. 4.; Report Writer: RM200 x 10 pages x 14 nexus; 28,000.00. B.; OPERATIONAL BUDGET. 5; Mileage Claim (RM150 x 5 pax x 14 nexus); 10,500.00. TOTAL; 259,700.00. |
| REVENUE (RM) – IF ANY Description: Income generated from the project | NA |
| RECOMMENDATION Description Required decision from the MPC Board of Management | The consideration and approval of the Board of Management (BOM) is sought to develop Business Supply Chain Frameworks for 14 Productivity Nexus with an estimated cost of RM249,200.00 utilizing SPC2.0 and RM10,500.00 utilizing operational budget. |
| UNIT/ DIVISION | DMO/MMT |

| Only for project/proposal using Development Budget from other Unit/Division. Ignore this column if it is not applicable. |  |  |
| --- | --- | --- |
| SUPPORTED BY: NAME OF OFFICER-IN-CHARGE FOR THE DEVELOPMENT BUDGET Designation: Budget Name: Date: |  |  |
| **Compulsory | **Compulsory | Proposals reviewed up to the supervisor level is adequate. Ignore this column if it is not applicable. |
| PREPARED BY: | REVIEWED BY: | VERIFIED BY: |
| NURUL SYAFIQAH ZAINUDIN ASSISTANT MANAGER | NUR HANIM ABD GHANI DEPUTY DIRECTOR |  |