## Slide 1
Workplan | 2024 |  |  |  | 
 | July | Aug | Sept | Oct | Nov
Phase 1: Baseline Drafting the Guideline on Tender Evaluation for Performance Based Contracts (Workshop 1) | 31 | 1 |  |  | 
Engagement with MOF, JKR, KKM |  | 9 | 25 |  | 
Phase 2: Validation Conducting validation sessions with both public and private Sectors (Workshop 2) Revise the Guideline to incorporate any feedback or recommendation received |  |  |  | 30 | 
Phase 3: PEMUDAH Submitting to PEMUDAH to get approval for Pilot Project |  |  |  |  | 
Phase 4: Pilot Project (MOH, JKR) Conducting a pilot project on the effectiveness of the guideline during the tender evaluation process Observing the outcomes of the pilot project |  |  |  |  |