Proposal for Board of MPC Management

| Title Keterangan: Tajuk Projek/ Cadangan | IoT-Driven Energy Monitoring System - piloting 10 manufacturing companies |
| --- | --- |
| Date / Time line Keterangan: Jadual mula dan akhir pelaksanaan projek/ cadangan | Mac – Dec 2025 |
| Purpose and Background Keterangan: Tujuan dan penerangan ringkas mengenai projek | The purpose of the projects are: - To guide the company through the process of improving energy management practices, reducing operational costs and staying compliant with latest regulations. - Enable companies to reduce operational costs through modern management practices and technology adoption. - Guide companies in enhancing energy management practices and ensuring compliance with current regulations. - Equip companies with IoT-based tools and expertise to improve energy efficiency monitoring. - Achieving a targeted 10% reduction in energy consumption, contributing to energy sustainability |
| Justification Keterangan: Penjelasan yang menyokong kepada pelaksanaan projek/ cadangan | - Improve Energy Intensity This project will help companies reduce energy consumption by using IoT Monitoring system. By improving energy efficiency, companies will lower operational costs, enhance productivity, and contribute to Malaysia’s World Competitiveness Ranking. - Prepare for Compliance Participants will gain skills in energy monitoring and reporting, avoiding penalties and ensuring smooth compliance This will prepare companies for the Energy Efficiency & Conservation Act 2024, ensuring they meet legal requirements |
| Method of Implementation Keterangan: Kaedah yang perlu dilakukan bagi melaksanakan projek | The project will be executed through a structured and phased approach, ensuring that participating companies gain practical knowledge and tools (ATTACHMENT 2). The key elements include - Capacity Building and Training - Conduct a comprehensive Awareness Seminar, Clinic, training workshop for participants, focusing on the development and implementation of the IoT Monitoring system. - Provide participants with practical tools, including an IoT Sensor for customizing and updating their energy management data. - Assessments and Monitoring - Implement assessments at the 10 participating companies to identify Significant Energy Uses (SEUs), analyze energy consumption patterns, and establish energy baselines. This will be followed by customized intervention strategies to reduce energy consumption by up to 10%, directly improving the Energy Intensity (EI) of each company. - Provide each company with access to a real-time energy monitoring portal that integrates smart energy analytics. This platform will help companies track their energy performance in real-time and make data-driven decisions for continuous improvement. - Reporting and Review - Performance reports will be generated to document energy savings, improvements in the Energy Intensity (EI) indicator and reporting international compliance, contributing to Malaysia’s World Competitiveness Ranking. |
| Stakeholders Keterangan: Pihak atau kumpulan yang menerima kesan positif mahupun negatif daripada projek yang dijalankan | - Ten companies from Automotive, Pharmaceutical Nexus or other NEXUS (2 person for each company) |
| Expected Outcome Keterangan: Apa yang MPC perlu capai/ faedah- faedah jangka pendek dan jangka panjang hasil dari intervensi projek/ cadangan | - Improved Energy Intensity (EI) Ranking: A 10% reduction in energy consumption, positively impacting Malaysia’s EI indicator and World Competitiveness Ranking. - Long-term Cost Savings: Companies will experience sustained operational cost savings through better energy management. Reduced Carbon Footprint: Companies will lower their carbon emissions, supporting Malaysia’s target of 45% carbon reduction by 2030 and net-zero by 2050. - Ensuring companies to compliance with the Energy Efficiency & Conservation Act 2024 and enhancing their ESG performance |
| Expected Output Keterangan:Output ketara dan tidak ketara yang dihasilkan daripada aktiviti projek/ cadangan. | - Real-Time Monitoring: Track energy usage in real- time, allowing for immediate detection of inefficiencies. - Data Analytics: Use AI to analyze energy consumption patterns, identify trends, and predict potential issues. - Customizable Alerts: Set up notifications for anomalies or inefficiencies, helping to prevent energy waste. - Integration: Compatible with other industrial systems, allowing for seamless data exchange and enhanced operational efficiency. |
| Target Audience Keterangan: Individu/ kumpulan yang menerima faedah daripada projek/ cadangan | 10 Manufacturing Companies |
| Source of Budget Keterangan: Sumber bajet / jumlah kos yang terlibat. | SPC 2.0; :; 187,000. Total; :; 187,000. Details budget (ATTACHMENT 1) |
| Income to MPC Keterangan: Pendapatan yang diterima daripada projek | Value creation RM100mil savings |
| Recommendation Keterangan: Keputusan yang diperlukan daripada Lembaga Pengurusan MPC | We seek the Board of Management’s approval of RM187,000 using SPC 2.0 budget to implement this pilot project on IoT-Driven Energy Monitoring System for 10 manufacturing companies |
| Unit/Division | MMT |

ATTACHMENT 1

Pilot Project on IoT-Driven Energy Monitoring System for Automotive and Pharmaceutical Nexus

|  | Phase and activities | RM |
| --- | --- | --- |
| A | Training Capacity Building (4 days) |  |
|  | Day 1: Introduction to Energy Monitoring Systems |  |
|  | Day 2: System Setup and Basic Configuration |  |
|  | Day 3: Using the Energy Monitoring Dashboard Day 4: Practical Applications and Review Package of Installation for each company - Installation the unit covered during training process - 3 no’s of Class 0.5 Current Transformer - IOT Connectivity included for 24 months - Platform access for 24 months (5 user per client) - Data Access via API for 24 months (1 API user) |  |
|  |  | 187,000 (RM17,000 x 10 companies) + 10% SST =170,000 + 17,000 =187,000 Per company =187,000/10 =18,700 |
|  | Grand Total | 187,000 |

*Note : RM18,700 per company

ATTACHMENT 2

Four Days Training Details of Pilot Project on IoT-Driven Energy Monitoring System

for Automotive and Pharmaceutical Nexus