IMPLEMENTATION TIMELINE

| Date | Status | Note |
| --- | --- | --- |
| 5 July | Discussion on outline | Secretariat |
| 10 July | Lantik penulis | Secretariat |
| 22 – 23 July | Mesyuarat Sebut harga B (designer/printer) Lantikan designer | PCT Secretariat |
| 25 July | Dapat Sijil Bersih | Kewangan |
| 26 July – 10 Aug | Write-up based on Sijil Bersih | Kewangan |
| 29 July | Come out with mock up design (cover & layout) | Designer |
| 10 Aug | Send content Kewangan to writer | Secretariat |
| 11 Aug | Combine all contents and send to Secretariat | Writer |
| 12 Aug | Send full content to all members JK1 | Secretariat |
| 15 Aug | Meeting JK1 to review full content BM | JK1 |
| 16 – 20 Aug | Editing post-JK1 and send to secretariat | Writer |
| 15 – 23 Aug | First draft of report (BM version) | Designer |
| 24 Aug | Hantar draf laporan kepada MITI | Secretariat |
| Before 25 Aug | Lantik Translator | Secretariat |
| 25 Aug – 9 Sep | Translation | Translator |
| Before 10 Sep | Lantikan Proofreader | Secretariat |
| 10 Sep | Send translation to writer | Translator |
| 10 Sep – 19 Sep | Proofreading Full Content BM and BI | Proofreader |
| 19 Sep | Writer sends full report to Secretariat | Writer |
| 20 Sep – 25 Sep | Finalise in layout and send to secretariat | Designer |
| 25 – 27 Sep | Checking and finalising (full design) | Secretariat |
| 27 Sep | Printing mock-up | Designer |
| 29 Sep | Mock-up ready | Designer |
| 30 Sep | Sit-in proofread mock-up – JK2 | All |
| 3 Oct | Approval KP MPC | Secretariat |
| 4 – 5 Oct | Edit changes from mock-up | Writer |
| 6 - 7 Oct | Edit on layout | Designer |
| 8 Oct | Send Final draft in layout | Designer |
| 8 - 10 Oct | Check by JK | JK, secretariat and writer |
| 10 Oct | Report printing | Designer |
| 14 Oct | Final copy ready and send to secretariat | Designer |
| 17 Oct | Hantar to MITI | Secretariat |