Lampiran 1 - Jadual Perancangan Projek

|  | Activities | Month |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | August | Sept | Oct | Nov | Dec |
| 1 | Administrative: - Preparation of BOM - Mesyuarat Sebut Harga B - Appointment of Interviewer & Writer | 15-24 |  |  |  |  |
| 2 | Interview sessions with PIC Projects (MyMudah, RIA, BI) | 24-30 |  |  |  |  |
| 3 | Presentation of Report Structure by Writer |  | 1-16 |  |  |  |
| 4 | Concept & Cover Page Designs (dummy text) |  | 19-30 |  |  |  |
| 5 | Submission of 1st draft with content layout |  |  | 1-7 |  |  |
| 6 | Editorial Team - Appointment of editorial team - Presentation edited draft to Top Management MPC |  |  | 8-15 |  |  |
| 7 | Submission of 2nd draft with content (editing) |  |  | 16-22 |  |  |
| 8 | Final check on report Proof-reading |  |  | 23-31 |  |  |
| 9 | Submission of Final draft to the Writer |  |  |  | 1-14 |  |
| 10 | Final Artwork |  |  |  | 15-30 |  |
| 11 | Upload report at MPC Website |  |  |  |  | 1-15 |